## 05-04-2022
Resource Name | Action Point / Impediments | Status | Comments
Archana M
Aravinth S
Atsaya A | System issue | informed to admin team
Vidhya Priya
Karthickraja S | No system available | informed to admin team
Aakaash M | System issue | informed to admin team
Jeevanandham | No system available | informed to admin team
Ajaybharathi | No system available | informed to admin team
Logesh
Madujith M A
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aakaash M | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Ajaybharathi K | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Aravinth S | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Archana M | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Atsaya A | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Jeevanantham N | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Karthickraja S | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Logesh Kumar K | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Madujith M A | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
VidhyaPriya V | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1

## 06-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | 1.Discussion about wire frame. 2.Designing wire frame for the Requester and Approver | 1.Drilled down the User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Discussion about the meeting. | wire framing for the UI of HR Page | 1,1,3,0.5,0.5 | 1
Ajaybharathi K | 1.Acceptance criteria 2.Constraints 3.Dependencies 4.assumptions | 1.Prepare a Flowchart for User Stories. 2.Meeting with Rafi. 3.Discussion about the meeting. | NIL | 4,1,0.5 | 1,1
Aravinth S | 1. wireframe for approver 2.Constraints 3.Dependencies | 1.Drilled down the User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Discussion about the meeting. | NIL | 3,1,0.5 | 1
Archana M | 1.discussion about wire frame . 2.made wire frame on Admin home page(manage employee,manage Award,manage Department). | 1.Meeting with rafi. 2.drilled down the user story. 3.Discussion about the meeting . 4.rework on flow diagram | wire framing for the UI of Admin | 1,1,3,0.5,0.5 | 1
Aakaash M | 1. Wire framing for the UI of Public pages. 2. Removed duplicates from the User Stories. | 1.Drilled down the User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Project Review. 5.Discussion about the meeting. | Wire framing for the UI of Dashboard | 2 - 1 - 1 | - 1 - 2 -
Jeevanantham N | 1.Acceptance criteria 2.Constraints 3.Dependencies 4.assumptions | 1.Prepare a Flowchart for User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Discussion about the meeting. | NIL | 4,1,0.5 | 1,1
Karthickraja S | 1.Discussion about wire frame. 2.Designing wire frame for the Requester and Approver | 1.Meeting with rafi. 2.drilled down the user story. 3.Discussion about the meeting . 4.rework on flow diagram | wire framing for the UI of HR Page | 1,1,3,0.5,0.5 | 1,1
Logesh Kumar K | 1. Designing wireframe for approver 2.Constraints | 1.Drilled down the User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Discussion about the meeting. | NIL | 3,1,0.5 | 1,1
Madujith M A | 1.Discussion about wire frame,2.Designing wire frame for the home page | 1.Drilled down the User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Discussion about the meeting. | NIL | 2 - 1 1 | - 2 - -
VidhyaPriya V | 1.Wireframe for Admin 2. | 1.Meeting with rafi. 2.drilled down the user story. 3.Discussion about the meeting . 4.rework on flow diagram | wire framing for the UI of Admin | 1,1,3,0.5,0.5 | 1,1
| Resource Name | Action Point / Impediments | Status | Comments
Archana M
Aravinth S
| Atsaya A | System issue | informed to admin team
VidhyaPriya V
| Karthickraja S | No system available | Informed to admin team
| Aakaash M | System issue | informed to admin team
| Jeevanantham N | No system available | informed to admin team
| Ajaybharathi | No system available | informed to admin team
Logesh
| Madujith M A | Pulling from Git and again uploading it to One drive inorder to edit Excel Sheet and again downloading from one drive and pushing back to the scm(GIT) seems to be a tedious process |  | Need access for excell desktop version

## 07-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | 1.Discussion on prototype. 2.Reworking on wire frame for the Requester (Award page,my request page)and Approver(Award page,my request page,approver page)AND HR page | 1.Meeting with rafi(wire frame) 2.Session on Abstract Factory Pattern. 3.rework on prototype | NIL | 0.5,5.5,1 | 1
Ajaybharathi K | 1. Acceptance criteria. 2.Dependencies. 3.Assumptions. | 1.Explored on git - How to clone, push ,pull . 2.Created acceptance criteria for all user stories. 3.Created assumptions for public user story. 4.Session on Abstract factory design pattern. 5.Meeting with Rafi. | NIL | 1-2-2-1 | 1
Aravinth S | 1. designing wireframe for dashboard 2.Constraints | 1. designed wireframe for approver 2. Explor about constraints 3.meeting with rafi (MOM) | NIL | 4,1,1 | 1
Archana M | 1.Discussion on prototype. 2.Reworking on wire frame for the Admin (Manage employee,manage Award,Manage Orz) | 1.Meeting with rafi(wire frame) 2.Session on Abstract Factory Pattern. 3.rework on prototype(ADMIN) | NIL | 0.5,5.5,1 | 1
Aakaash M | Redesigning the home page, Dashboard in Admin page | 1)Designed Wireframe for the Public and Approver pages 2)Discussion about redesigning the wireframe 3)Session about design pattern (abstract factory) | Wire framing for the UI of HR page | 4 1 | - - 2
Jeevanantham N | 1.Acceptance criteria 2.Dependencies 3.Assumptions | 1.Explored on git - How to clone, push ,pull . 2.Created acceptance criteria for all user stories. 3.Created assumptions for public user story. 4.Session on Abstract factory design pattern. 5.Meeting with Rafi. | NIL | 1-2-2-1 | 1
Karthickraja S | 1.Discussion on prototype. 2.Reworking on wire frame for the Requester (Award page,my request page)and Approver(Award page,my request page,approver page)AND HR page | 1.Meeting with rafi(wire frame) 2.Session on Abstract Factory Pattern. 3.rework on prototype | NIL | 0.5,5.5,1 | 1
Logesh Kumar K | 1. Designing wireframe for dashboard 2.Constraints | 1. designed wireframe for approver 2. Explor about constraints 3.Explore about prototype design pattern | NIL | 4,1,1 | 2
Madujith M A | Redesinging the Home page wireframe | 1).Designed homepage wireframe. 2)Explored about Prototype design pattern.3)Disscussion meeting about redesigning the wireframe 4) Dessign pattern session( abstract factory) | NIL | 3 - 1 | - 2 - 1
VidhyaPriya V | 1.Discussion on prototype. 2.Reworking on wire frame for the Admin (Manage employee,manage Award,Manage Orz) | 1.Meeting with rafi(wire frame) 2.Session on Abstract Factory Pattern. 3.rework on prototype(ADMIN) | NIL | 0.5,5.5,1 | 1

## 08-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | 1.Reworked on Wireframe for Approver 2.Discussion About Meeting with Team 3.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Session on DesignPattern - Builder,Prototype. 3.Rework on prototype(Approver) | NIL | 2-2-1-2 | 1
Ajaybharathi K | 1.Wireframe For HR 2.Design Admin Dashboard. | 1. Assumptions for Public 2. Git Explore 3. Session on Design Pattern - Builder, Prototype 4. Meeting with Rafi(MOM) 5. Discussion About the Meeting with Team. | NIL | 1-2-2-1 | 1
Aravinth S | 1. designing wireframe for dashboard 2.Constraints | 1. designed wireframe for approver 2. Explor about constraints 3.meeting with rafi (MOM) | NIL | 4,1,1 | 1
Archana M | 1.Reworked on Wireframe for Admin(Manage employee,Manage Award,Manage Orz) 2.Discussion About Meeting with Team 3.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Session on DesignPattern - Builder,Prototype. 3.Rework on prototype(Admin) | NIL | 2-2-1-2 | 1
Aakaash M | Improving the wireframe with neat flow | 1)Designed wireframe of homepage and Login screen for each users. 2)Session about Prototype design pattern. 3)Disscussion meeting about Wire Frame 4)Discussion meeting about redesigning the wireframe and spliting the work between teams | Nil | 4 - 1 1 | - 1
Jeevanantham N | 1.Wireframe For HR 2.Design Admin Dashboard | 1. Assumptions for Public 2. Git Explore 3. Session on Design Pattern - Builder, Prototype 4. Meeting with Rafi(MOM) 5. Discussion About the Meeting with Team. | NIL | 1-2-1-1-1 | 1
Karthickraja S | 1.Reworked on Wireframe for Requester. 2.Discussion About Meeting with Team. 3.Rechecked All Wireframes. | 1.Meeting with rafi(wire frame) 2.Session on DesignPattern - Builder,Prototype. 3.Rework on prototype(requester) | NIL | 2-2-1-2 | 1
Logesh Kumar K | 1. Designing wireframe for dashboard 2.Constraints | 1. designed wireframe for approver 2. Explor about constraints 3.Explore about prototype design pattern | NIL | 4,1,1 | 2
Madujith M A | Redesinging the Home page wireframe, Desiging poster for the published award | 1).Designed homepage and sidebar wireframe. 2)Session about Prototype design pattern.3)Review meeting with Rafi about redesigning the wireframe 4) discussion meeting about redesigning the wireframe and spliting the work between teams | NIL | 4 - 1 - | - 1 - 1
VidhyaPriya V | 1.Reworked on Wireframe for Admin(Manage employee,Manage Award,Manage Orz) 2.Discussion About Meeting with Team 3.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Session on DesignPattern - Builder,Prototype. 3.Rework on prototype(Admin) | NIL | 2-2-1-2 | 1

## 09-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | 1.Reworked on Wireframe for Requester(award,request,profile) and approver (award,approve,request,profile). 2.Discussion About Meeting with Team. 3.Rechecked All Wireframes. | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Approver) | NIL | 4-0.5-1-1.5-2 | -
Ajaybharathi K | 1.Wireframe For HR 2.Rechecked Admin ManageOrganization | 1. Wireframe for HR 2. Recheck on Wireframe Approver Requester 3. Meeting with Rafi(MOM) 4. Discussion About the Meeting with Team. | NIL | 3-1-2-1 | 1
Aravinth S | 1. Redesigning wireframe for dashboard | 1. designed wireframe for Dashboard 2.meeting with rafi (MOM) | NIL | 4,2 | NIL
Archana M | 1.Reworked on Wireframe for Admin(Home page,Manage employee,Awards,Organization,Department) 2.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Admin)3.Discussion about Meeting with team(Wireframe) | NIL | 2,1,2,2,1 | -
Aakaash M | Developing the workflow of the homepage wireframe and desgining the login workflow | 1)Brain Storming with team for - 1 hour. 2).Refining the Home page and lading page wireframes - 2 hours | Nil | 3 hrs | -
Jeevanantham N | 1.Wireframe For HR 2.Rechecked Admin Manage Employee | 1. Wireframe for HR 2. Recheck on Wireframe Approver Requester 3. Meeting with Rafi(MOM) 4. Discussion About the Meeting with Team. | NIL | 3-1-2-1 | 1
Karthickraja S | 1.Reworked on Wireframe for Requester(award,request,profile) and approver (award,approve,request,profile). 2.Discussion About Meeting with Team. 3.Rechecked All Wireframes. | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Requester) | NIL | 4-0.5-1-1.5-2 | -
Logesh Kumar K | 1. Redesigning wireframe for dashboard | 1. designed wireframe for Dashboard 2.meeting with rafi (MOM) | NIL | 4,2 | NIL
Madujith M A | Developing the workflow of the homepage wireframe and desgining the login workflow | 1)Brain Storming with team 2).Refining the Home page and landing page wireframes 3) discussion meeting about redesigning the wireframe and spliting the work between teams | NIL | 1 4 1 | -
VidhyaPriya V | 1.Reworked on Wireframe for Admin(Home page,Manage employee,Awards,Organization,Department) 2.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Admin) 3.Project review 4.Discussion about Meeting with team(Wireframe) | NIL | 4,2,2,2,1,1 | 1
| Resource Name | Action Point / Impediments | Status | Comments
Archana M
Aravinth S
| Atsaya A | System issue | informed to admin team
VidhyaPriya V
| Karthickraja S | No system available | Informed to admin team
| Aakaash M | System issue | informed to admin team
| Jeevanantham N | No system available | informed to admin team
| Ajaybharathi | No system available | informed to admin team
| Logesh | No system available | informed to admin team
| Madujith M A | Pulling from Git and again uploading it to One drive inorder to edit Excel Sheet and again downloading from one drive and pushing back to the scm(GIT) seems to be a tedious process |  | Need access for excell desktop version

## 11-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | 1.Reworked on Wireframe for Requester(award,request,profile) and approver (award,approve,request,profile). 2.Discussion About Meeting with Team. 3.Rechecked All Wireframes. | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Approver) | NIL | 4-0.5-1-1.5-2 | -
Ajaybharathi K | 1.Wireframe For HR 2.Rechecked Admin ManageOrganization | 1. Wireframe for HR 2. Recheck on Wireframe Approver Requester 3. Meeting with Rafi(MOM) 4. Discussion About the Meeting with Team. | NIL | 3-1-2-1 | 1
Aravinth S | 1. Redesigning wireframe for dashboard | 1. designed wireframe for Dashboard 2.meeting with rafi (MOM) | NIL | 4,2 | NIL
Archana M | 1.Reworked on Wireframe for Admin(Home page,Manage employee,Awards,Organization,Department) 2.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Admin)3.Discussion about Meeting with team(Wireframe) | NIL | 2,1,2,2,1 | -
Aakaash M | Developing the workflow of the homepage wireframe and desgining the login workflow | 1)Brain Storming with team for - 1 hour. 2).Refining the Home page and lading page wireframes - 2 hours | Nil | 3 hrs | -
Jeevanantham N | 1.Wireframe For HR 2.Rechecked Admin Manage Employee | 1. Wireframe for HR 2. Recheck on Wireframe Approver Requester 3. Meeting with Rafi(MOM) 4. Discussion About the Meeting with Team. | NIL | 3-1-2-1 | 1
Karthickraja S | 1.Reworked on Wireframe for Requester(award,request,profile) and approver (award,approve,request,profile). 2.Discussion About Meeting with Team. 3.Rechecked All Wireframes. | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Requester) | NIL | 4-0.5-1-1.5-2 | -
Logesh Kumar K | 1. Redesigning wireframe for dashboard | 1. designed wireframe for Dashboard 2.meeting with rafi (MOM) | NIL | 4,2 | NIL
Madujith M A | Developing the workflow of the homepage wireframe and desgining the login workflow | 1)Brain Storming with team 2).Refining the Home page and landing page wireframes 3) discussion meeting about redesigning the wireframe and spliting the work between teams | NIL | 1 4 1 | -
VidhyaPriya V | 1.Reworked on Wireframe for Admin(Home page,Manage employee,Awards,Organization,Department) 2.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Admin) 3.Project review 4.Discussion about Meeting with team(Wireframe) | NIL | 4,2,2,2,1,1 | 1
| Resource Name | Action Point / Impediments | Status | Comments
Archana M
Aravinth S
| Atsaya A | System issue | informed to admin team
VidhyaPriya V
| Karthickraja S | No system available | Informed to admin team
| Aakaash M | System issue | informed to admin team
| Jeevanantham N | No system available | informed to admin team
| Ajaybharathi | No system available | informed to admin team
| Logesh | No system available | informed to admin team
| Madujith M A | Pulling from Git and again uploading it to One drive inorder to edit Excel Sheet and again downloading from one drive and pushing back to the scm(GIT) seems to be a tedious process |  | Need access for excell desktop version

## 12-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | Data Model | Discussion with team. | NIL | 1 hr 15 mins | -
| Rechecked all WireFrame | wireframe for approver(changed naming conventions,flow for rejection reason) |  | 1 hr
|  | check on wireframe for HR |  | 1 hr 30 mins
|  | checked wireframe for admin(refined flow for awards,employee,department) |  | 1 hr 30 mins
Ajaybharathi K | Data Model Table | Discussion with Team | NIL | 1hr 15 mins
|  | Data Model 1st Version |  | 3 hrs
1 hr
Aravinth S | Data Model Table | entering MOM For Last 2 days | NIL | 1/2 hr
|  | Meeting with team regarding wireframe (Approver) |  |  | 1/2 hr
| Reviewing Data model | Anitha Session |  | 1/2 hr
Reviewing the Flow of the Wireframe (All)
Archana M | Rechecked all WireFrame | Discussion with team. | NIL | 1 hr 15 min
|  | Rechecked wireframe for admin(refined flow for awards,employee,department) |  | 1.5
|  | MVC Application Review |  |  | 1.5
|  | Session with Anitha |  |  | 0.5
Aakaash M | Data Models - Relationship | Entity and Operations for data model - 2hrs
Had a discussion with team - 1.15hrs
|  | Gone through the wire frames - 1hrs | NIL | 4.5hrs
Jeevanantham N | Redesign Dashboard | Discussion with Team |  | 1 hrs
|  | Rechecked for Approver, Admin Flow |  | 2
|  | Session with Anitha |  | 1
|  | Data Model |  | 1
Karthickraja S | Data Model | Discussion with team. | NIL | 1 hr 15 mins
| Rechecked all WireFrame | wireframe for approver(changed naming conventions,flow for rejection reason) |  | 1 hr
|  | check on wireframe for HR |  | 1 hr 30 mins
|  | checked wireframe for admin(refined flow for awards,employee,organisation,department) |  | 1 hr 30 mins
Logesh Kumar K |  |  | NIL
| Data model Review | Discussion with Team |  | 1hr 15 mins
| Data Model Table | Review the flow for all wireframes. |  | 1 hr
Madujith M A |  | 2 hr redesigning the DashboardDiscussion with team. |  | 1 hour 15 mins
| Dashboard redesign | redesigning the Dashboard |  | 3 hours
|  | project presentation |  |  | 1 hour
VidhyaPriya V |  |  | NIL
| NIL | Discussion with Team |  | 1 hour | NIL

## 13-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | sample data for data model(excel sheet) | Discussion with team. | NIL | 30mins | -
|  | wireframe for approver(changed naming conventions,Add request) |  | 1 hr
|  | refined the user story |  | 1hr30mins
|  | College review |  | 30mins
|  | Meeting with Rafi( About Lesson,data model.physical model,view model ) |  | 1 hr 15 mins
|  | checked wireframe for admin(refined flow for awards,employee,department) |  | 1 hr
Ajaybharathi K | Data Model Table | Discussion with Team | NIL | 30 mins
|  | Normalisation |  | 1 hr
|  | Physical Data Model |  | 2hr 30mins
|  | Meeting with Rafi( plan for next 3days ) |  | 1hr
Aravinth S |  | entering MOM For Last day | NIL | 1/2 hr
|  | Logo removed for all wireframe pages some alignment corrections |  | 1/2 hr
|  | Session about lesson learned (planning for 4 days - Services, Operations, class diagram, view model) |  |  | 1 hr
| Refining Constraints, dependencies for each user story |  |  | 2 hr
Archana M |  | Discussion with team. | NIL | 30mins
| Normalization | Rechecked wireframe for admin(refined flow for awards,employee,department) |  | 1hr30mins
|  | refined the user story |  | 1hr30mins
|  | Meeting with Rafi( About Lesson,data model.physical model,view model ) |  |  | 1hr15mins
Aakaash M | Dashboard modiications | Rechecked the Prototype with the last MOM - 1hr | NIL | 3.5hrs | 15mins
Had a discussion with team - 1.15hrs
Discussed and implemented the Physical model - 1hrs
Jeevanantham N | Redesign Dashboard | Discussion with Team |  | 30mins
|  | Project Review Preparation |  | 2 hr
|  | Normalisation |  | 1 hr
|  | Project Review |  | 40 min
|  | Checked Admin flow |  | 1 hr
Karthickraja S | sample data for data model(excel sheet) | Discussion with team. | NIL | 30mins | -
|  | wireframe for requester(Add Request) |  | 30min
|  | rechecked wireframe for approver(Add Request,changed naming conventions) |  | 1 hr
|  | wireframe for HR(Add Request) |  | 1 hr
|  | Meeting with Rafi( About Lesson,data model.physical model,view model ) |  | 1.15min
|  | rechecked wireframe for admin(refined flow for awards,employee,organisation,department) |  | 1 hr 30 mins
Logesh Kumar K |  |  | NIL
|  | Learned normalization concepts |  | 1 hr
| Refining use cases(dependencies,constraints) | Discussion with team. |  | 30 mins
|  | Session with Rafi about Lessions learned in project training and what to do for next 7 days |  |  | 1 hr
Madujith M A |  | Discussion with team. |  | 1 hour 15 mins
| Dashboard redesign | redesigning the Dashboard |  | 3 hours
|  | Session with Rafi regarding lessons learned and what we are going to do till next mid week |  |  | 1 hour
VidhyaPriya V |  | Discussion with team. | NIL | 30mins
|  | Rechecked wireframe for admin(refined flow for awards,employee,department) |  | 1hr30mins
| Normalization | Refined the user story |  | 1hr30mins
|  | Meeting with Rafi( About Lesson,data model,physical model,view model ) |  |  | 1hr15mins

## 16-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  |  | NIL | - | -
| Absent | Absent
Ajaybharathi K |  |  | NIL
|  | Reworked on DataModelling |  | 2hours
Aravinth S |  |  | NIL
|  | recap about Exception handling in C# |  | - | 1 hr
| Entity Framework |  |  |  | 1 hr
Archana M |  |  | NIL
| Angular |  |  | 2hr
|  | Explored C# |  |  | 2hr
Aakaash M |  |  | NIL | 3.5hrs | 1
| HLD, Angular | Worked on dashboard - Features - 3hrs
Explored about implementing Graph - 1hr
Jeevanantham N |  |  | NIl
| HLD | C# Explore |  | 1hr | 4hr
What is Web API ?
Karthickraja S |  | created home page (HTML,CSS,BOOTSTRAP) | NIL | 3.5HRS
Logesh Kumar K |  |  | NIL
| Entity Framework | Explore about HLD |  | 2hr | 1hr
| Angular |  |  |  | 1 hr
Madujith M A
|  | redesigning the Dashboard with date filter,altering the fields(x-axis) |  | 3 hours
|  | Exploration about angular and dashboard integration using angular |  |  | 1 hour
VidhyaPriya V |  |  | NIL
|  | refined the Datamodel |  | 2 hours | 2 hours
Angular

## 18-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  |  | NIL | - | -
| Absent | Absent
Ajaybharathi K |  | Discussion with Team about HLD | NIL | 1hour
|  | Data Dictionaries And View model in HLD |  | 2 hour
|  | Modules and Features in HLD |  | 30 mins
Aravinth S |  |  | NIL
| Absent | absent |  | - | -
Archana M |  | Discussion with team about HLD | NIL | 1
|  | working on Award home page (HTML) |  | 4hr
|  | Discussion with team. |  | 1hr
| Angular |  |  |  | 1hr15mins
Aakaash M |  | Discussion with Team - 1.30hrs | NIL | 4.5hrs | 1
| HLD, Angular | Worked on HLD - Features - 3hrs
Explored and collected information on Facade design pattern - 1hr
Jeevanantham N | HLD | Discussion with Team about HLD | NIl | 2hr30mins
| Angular | C# Access Modifiers with Examples |  | 1hr | 40mins
| Web API | Web API Sample Project Understanding |  | 2hr30mins
Karthickraja S | Angular | Discussion with team about HLD | NIL | 1hr | 1hr
|  | working on Award home page (HTML) |  | 4 hrs
|  | Discussion with team. |  | 1hr
Logesh Kumar K |  |  | NIL
| Absent | Absent |  | -
Madujith M A |  | Discussion with team. |  | 1 hour
|  | Worked on HLD - Features |  | 3 hours
|  | Exploration in angular |  |  | 1 hour
VidhyaPriya V |  | Discussion with team about HLD | NIL | 1 hour
|  | Modules and Features in HLD |  | 1 hour
| Angular | View Model in HLD |  | 1 hour | 1hour
| HLD |  |  |  | 1 hour

## 19-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  |  | NIL | - | -
| Absent | Absent
Ajaybharathi K |  | Standup Meeting | NIL | 30mins
| Web API | Explored on how to create Webapi |  | 30 minutes
|  | Explored on Typescript |  | 30 minutes
| System Architecture in HLD |  |  | 1hour
| Services in HLD |  |  | 1hour
Aravinth S |  | Standup Meeting | NIL | 30mins
| EF | Discussion with team about Yesterday (18-04-2022) activities (HLD) |  | 30 minutes | 2 hr
| Typescript | Typescript sample program Assignment |  |  | 30 mins
Archana M | Typescript (sample program) | Standup Meeting | NIL | 30mins | 1hr
|  | Recollected the basic concepts(oops,datatype,sql,access modifiers,constructor) |  | 3.5 hrs
|  | Discussion about services |  | 30mins
Aakaash M |  | Standup Meeting - 1hr | NIL | 4.5hrs | 1
| HLD, HTML Layouts | Explored Type Script - 1.5hrs
HTML layout for Login page - 2hrs
Jeevanantham N |  | Standup Meeting | NIl | 30mins
|  | Review the Features and Modules |  | 1hr
|  | Typescript (sample program) |  |  | 1hr
| Web API |  |  |  | 2hr
Karthickraja S |  | Standup Meeting | NIL | 30mins | 1hr
| Typescript (sample program) | Recollected the basic concepts(oops,datatype,sql,access modifiers,constructor) |  | 3.5 hrs
|  | Discussion about services |  | 30mins
Logesh Kumar K |  |  | NIL
|  | Standup meeting about HLD |  | 30 mins
| Typescript | Write the typescript sample program |  | 30 mins | 1 hr
|  | Explore about angular |  |  | 1 hr
Madujith M A |  | Standup Meeting |  | 30mins
|  | Exploration about Type script |  | 3 hours
|  | Exploration about angular and dashboard integration using angular |  |  | 1 hour
VidhyaPriya V |  | Standup Meeting | NIL | 30mins
|  | Explored on Web API |  | 1 hour
| Angular | Done Typescript sample program |  | 1 hour | 1hour
| HLD |  |  |  | 1 hour

## 20-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  |  | NIL | - | -
| Absent | Absent
Ajaybharathi K |  | Standup Meeting | NIL | 30mins
| HLD | Softskills |  | 1hour
|  | Session with Rafi about Web API, Html layout, HLD. |  | 45 mins
Aravinth S |  | Standup Meeting with team about HLD | NIL | 30mins
| recap the Web API, EF | Softskills session |  | 1 hr | 30 mins
| Typescript | Session with Rafi about the work plan for this week (Web API, Html layout, HLD) |  | 45 mins | 1 hr
Archana M |  | Standup Meeting | NIL | 30mins | 1hr
Referred the HLD Document
|  | Soft skill session with Jaya |  | 1 hr
|  | Completed MOM |  | 20mins
|  | Session with Rafi Work plan for upcoming days(HLD,HTML layouts as per prototype) |  | 45mins
Aakaash M |  | Standup Meeting | NIL | 4.5hrs | 1
| HTML layouts | Softskill session - 1hr
HTML layout for Login and forgot password screen
Jeevanantham N |  | Standup Meeting | NIl | 30mins
|  | Review the Features and Modules |  | 1hr
|  | Typescript (sample program) |  |  | 1hr
| Web API |  |  |  | 2hr
Karthickraja S |  | Standup Meeting | NIL | 30mins | 1hr
|  | Referred the HLD Document |  | 1 hr
|  | Soft skill session with Jaya |  | 1 hr
|  | Completed MOM |  | 20mins
|  | Session with Rafi Work plan for upcoming days(HLD,HTML layouts as per prototype) |  | 45mins
Logesh Kumar K |  | Standup meeting about HLD | NIL | 30 mins
|  | Softskills session |  |  | 1 hr
| Web API | Explore HLD about dependency, layers,third party integration |  | 2 hr
|  | Session with Rafi about the work plan for this week (Web API, Html layout, HLD) |  | 45 mins
Madujith M A |  | Standup Meeting | NIL | 30mins
|  | Exploration about Type script |  | 3 hours
|  | Softskill session |  |  | 1 hour
|  | Session with Rafi about the work plan for this week (Web API, Html layout, HLD) |  | 45mins
VidhyaPriya V |  | Standup Meeting | NIL | 30mins
|  | Soft skill session with Jaya |  | 1 hour
| Angular | Session with Rafi on HLD and discussed workplan for this week(HLD,HTML Layout,Web API) |  | 45 mins | 1hour
| Services in HLD |  |  |  | 2 hours

## 21-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  |  | NIL | - | -
| Absent | Absent
Ajaybharathi K |  | Standup Meeting | NIL | 30mins
| HLD | Discussed on Prototype with Team |  | 1hr 30mins
|  | Worked on datamodel operations |  | 2hrs
|  | Meet Rafi for Project clarification(Status, Delete) |  | 10mins
Aravinth S |  | Standup Meeting | NIL | 30mins
| recap about Architecture pattern in ppt | Prototype review with team |  | 1 hr 30 mins
|  | DataModel Reviewed |  | 30 mins
Archana M |  | Standup Meeting | NIL | 30 mins
|  | Reviewed the prototype with team |  | 1 hr 30 mins
|  | Reviewed DataModel and services |  | 1 hr 30 mins
| HLD(NFR) |  |  |  | 1hr
Aakaash M |  | Standup Meeting - 30 mins | NIL | 3hrs
| Physical Model | Reviewed Prototype with team - 1.30hrs
Reworked on Data model - 1 hr
Jeevanantham N |  | Standup Meeting | NIl | 30mins
|  | Reviewed Prototype with team |  | 1hr30mins
| Services | Reviewed DataModel |  | 1hr
| Web API | Discussed about services |  | 2hrs | 1hr
Karthickraja S |  | Standup Meeting | NIL | 30mins
| HLD(Services) | Reviewed Prototype with team |  | 1hrs30mins
|  | Reworked on Data model |  | 2hrs
|  | Dicussed about Services |  | 30mins
|  | Meet Rafi for Project clarification(Status, Delete) |  | 10mins
Logesh Kumar K |  | Standup meeting | NIL | 30 mins
| Data Model Operations | Reviewed the prototype |  | 1 hr 30 mins
|  | College reward points Review meeting |  |  | 30 mins
Madujith M A |  | Standup Meeting | NIL | 30 mins
| Physical model | reviewing the prototype |  | 1 hour
|  | Discusssing the MOM,about the status disabling feature |  | 1hour
|  | Helping to do the datamodel |  | 1 hour
VidhyaPriya V |  | Standup Meeting | NIL | 30 minutes
|  | Reviewed the complete flow of the prototype |  | 1 hours 30 minutes
| Non functional requirements | Rework on Data model |  | 1 hour | 1 hour