## 11-04-2022
MOM | Status
In Public Home Page use "Filter" naming conversion instead of "Sort" | Yes
Avoid Scroll down pages just you can use paging | Yes
Use "Awardee" instead of "Nominee" - Naming Conversions | Yes
Select Name from the designation selection Instead of typing Employee name | Yes
Need flow for viewing the rejection Reason given by Approver in Approver's Page | Yes
Change filter's functionality in dashboard | In Progress
Start developing the Data Model | Yes

## 12-04-2022
MOM | Status
Remove Logo in Header | Yes
Don't Allow Public to Comment on any post in home page before login (Even don't allow the public to enter something in textbox) | Yes
Remove Forgot Password Checkbox in Forgot Password page | Yes
Correct All Alignment problem | Yes
Remove Remember Me Checkbox in Requester login page | Yes
If Requester Enter Any comment on any post it shows "me" (Avoid Requester name) and then what comment he gave | Yes
Correct the Breadcrumps in Requester's my award page
Remove Filter Retain Functionality | Yes
Remove ACE ID dropdown box in Add an request page (instead use name or username) | Yes
Remove Preview Functionality in awardee preview in requester page | Yes
rejection reason box have only close button(remove yes no ) | Yes
Remove Disable functionality in Dashboard Department filter | Yes
Use Stacked bar in dashboard | Yes
map the designation and department in data model | Yes
Remove Approver table in data model (refinment) | Yes
Start developing Physical model of data model | In Progress

## 13-04-2022
MOM | Status
Spelling corrections in wire frame | Yes
Alignments in wire frame | Yes
Removed Dropdown for Awards in Add Request | Yes
Date range filters in the dashboard | Yes
Relationship should not exist between Comment and emloyee in Data Model | Yes
change the Column name of PostId as AwardRequestId | Yes
Include the audit Fields | Yes
Changes in graph (x-axis Organisation) | No
Refine the operations in data model | Yes

## 20-04-2022
MOM | Status
Change datatype of the AddedBy, UpdatedBy Attributes in Award Request Table in DataModel | Yes
Spelling Correction - "Designation" | Yes
Operations in datamodel must contain Input and Output | Yes
Change FilterByAward(Award) into FilterByAward(Award type) | Yes
Naming convention - View Comments (plural) | Yes
Don't use remove functionality , instead use disable functionality | Yes
Analyse the differece between GetAwardRequest and ViewPost | Yes
Add Login and Logout operations in datamodel | Yes

## 21-04-2022
MOM | Status
Need one more Attribute in both Organisation and Department entity (Operation for getting list of departments under one specific organisation) | Yes
Multiple filters simultaneously | No
GetByStatus , PostView redundancy | Yes
Naming convention - Award Request become Award and Award becomes Award Type | Yes
Write operation in Status Entity | Yes
Need Designation ID, Department ID, ACE ID in Employee Entity | Yes
Logout's input and output method
Pass objects instead of IDs | Yes

## 22-04-2022
MOM | Status
Remove Period Parameter instead use fromdate - todate | Yes
Naming convention - Use "GetAwardByStatus" from "GetByStatus" in Award Entity | Yes
GetMyAward(Status) - include paramenters what is required | Yes
Need Cross cutting layer in System Architecture | No
Keep Organisation, Department, Designation as a separate service | Yes
Interaction diagram should contain all relevant services | Yes

## 23-04-2022
MOM | Status
All TextBox size must Same | yes
All Button size must same | yes
Dropdown is look like Button have to change | yes
Include sort by period in html home page | No
Rectify spacing problem | yes
Rectify Alignment problem | yes
Rework on system architecture and complete it | No
Complete Web API | No

## 25-04-2022
MOM | Status
List out the pages in your system | yes
Static page in GitHub | no
Estimation work | yes

## 26-04-2022
Action | Status
Publish html layout in GIT | yes
Summary
2 day once Do Code mering & Integration testing
no adhoc review
Gothrough PPT in a daily basis
Explore EF, Bootstrap
Time Sheet should be Low Level
don't skip review
Minimum it takes 2 days for implement one task
Team Members | Responsible for
Atsaya | Timesheet
Ajay, Jeeva | Web API
Archana | Review Scheduling
Logesh | HTML
Vedhya | Git
Aravinth | MOM

## 27-04-2022
Action | Status
Need Award Discription | Yes
Include Thumbnails | No
Prortotype should be updated if we made any changes in html | No
Avoid Horizontal Scroll bars | Yes
Broden Awardee details page, Requester List, and Admin pages | Yes
Utlize white spaces (real-estate) | No
Individual page estimation should contain no. of hrs and no. of days | No
HTML page cover All Functionality | Yes
Reuse the estimation hrs from other pages | No
if we assume like need extra hrs that should come in buffer | No
disable take less number of hrs and days refine it | No
All view functionality take less no of days and hrs and there is need only few hrs for html validation | No

## 28-04-2022
Action | Status
Need Audit fields in Admin too | Yes
Services, Repository should completed in Web API | Yes
Responsiveness, Gap problems, Consistancy | Yes
Do submit comment with enter button without having button | While Implementation

## 29-04-2022
Action | Status
Responsiveness of layout | Yes
Web Api | Yes
Logging and Exception handling | Yes