## 11-04-2022
MOM | Status
In Public Home Page use "Filter" naming conversion instead of "Sort" | Yes
Avoid Scroll down pages just you can use paging | Yes
Use "Awardee" instead of "Nominee" - Naming Conversions | Yes
Select Name from the designation selection Instead of typing Employee name | Yes
Need flow for viewing the rejection Reason given by Approver in Approver's Page | Yes
Change filter's functionality in dashboard | In Progress
Start developing the Data Model | Yes

## 12-04-2022
MOM | Status
Remove Logo in Header | Yes
Don't Allow Public to Comment on any post in home page before login (Even don't allow the public to enter something in textbox) | Yes
Remove Forgot Password Checkbox in Forgot Password page | Yes
Correct All Alignment problem | Yes
Remove Remember Me Checkbox in Requester login page | Yes
If Requester Enter Any comment on any post it shows "me" (Avoid Requester name) and then what comment he gave | Yes
Correct the Breadcrumps in Requester's my award page
Remove Filter Retain Functionality | Yes
Remove ACE ID dropdown box in Add an request page (instead use name or username) | Yes
Remove Preview Functionality in awardee preview in requester page | Yes
rejection reason box have only close button(remove yes no ) | Yes
Remove Disable functionality in Dashboard Department filter | Yes
Use Stacked bar in dashboard | Yes
map the designation and department in data model | Yes
Remove Approver table in data model (refinment) | Yes
Start developing Physical model of data model | In Progress

## 13-04-2022
MOM | Status
Spelling corrections in wire frame | Yes
Alignments in wire frame | Yes
Removed Dropdown for Awards in Add Request | Yes
Date range filters in the dashboard | Yes
Relationship should not exist between Comment and emloyee in Data Model | Yes
change the Column name of PostId as AwardRequestId | Yes
Include the audit Fields | Yes
Changes in graph (x-axis Organisation) | No
Refine the operations in data model | Yes

## 20-04-2022
MOM | Status
Change datatype of the AddedBy, UpdatedBy Attributes in Award Request Table in DataModel | Yes
Spelling Correction - "Designation" | Yes
Operations in datamodel must contain Input and Output | Yes
Change FilterByAward(Award) into FilterByAward(Award type) | Yes
Naming convention - View Comments (plural) | Yes
Don't use remove functionality , instead use disable functionality | Yes
Analyse the differece between GetAwardRequest and ViewPost | Yes
Add Login and Logout operations in datamodel | Yes

## 21-04-2022
MOM | Status
Need one more Attribute in both Organisation and Department entity (Operation for getting list of departments under one specific organisation) | Yes
Multiple filters simultaneously | No
GetByStatus , PostView redundancy | Yes
Naming convention - Award Request become Award and Award becomes Award Type | Yes
Write operation in Status Entity | Yes
Need Designation ID, Department ID, ACE ID in Employee Entity | Yes
Logout's input and output method
Pass objects instead of IDs | Yes

## 22-04-2022
MOM | Status
Remove Period Parameter instead use fromdate - todate | Yes
Naming convention - Use "GetAwardByStatus" from "GetByStatus" in Award Entity | Yes
GetMyAward(Status) - include paramenters what is required | Yes
Need Cross cutting layer in System Architecture | No
Keep Organisation, Department, Designation as a separate service | Yes
Interaction diagram should contain all relevant services | Yes

## 23-04-2022
MOM | Status
All TextBox size must Same | yes
All Button size must same | yes
Dropdown is look like Button have to change | yes
Include sort by period in html home page | No
Rectify spacing problem | yes
Rectify Alignment problem | yes
Rework on system architecture and complete it | No
Complete Web API | No

## 25-04-2022
MOM | Status
List out the pages in your system | yes
Static page in GitHub | no
Estimation work | yes

## 26-04-2022
Action | Status
Publish html layout in GIT | yes
Summary
2 day once Do Code mering & Integration testing
no adhoc review
Gothrough PPT in a daily basis
Explore EF, Bootstrap
Time Sheet should be Low Level
don't skip review
Minimum it takes 2 days for implement one task
Team Members | Responsible for
Atsaya | Timesheet
Ajay, Jeeva | Web API
Archana | Review Scheduling
Logesh | HTML
Vedhya | Git
Aravinth | MOM

## 27-04-2022
Action | Status
Need Award Discription | Yes
Include Thumbnails | No
Prortotype should be updated if we made any changes in html | No
Avoid Horizontal Scroll bars | Yes
Broden Awardee details page, Requester List, and Admin pages | Yes
Utlize white spaces (real-estate) | No
Individual page estimation should contain no. of hrs and no. of days | No
HTML page cover All Functionality | Yes
Reuse the estimation hrs from other pages | No
if we assume like need extra hrs that should come in buffer | No
disable take less number of hrs and days refine it | No
All view functionality take less no of days and hrs and there is need only few hrs for html validation | No

## 28-04-2022
Action | Status
Need Audit fields in Admin too | Yes
Services, Repository should completed in Web API | Yes
Responsiveness, Gap problems, Consistancy | Yes
Do submit comment with enter button without having button | While Implementation

## 29-04-2022
Action | Status
Responsiveness of layout | Yes
Web Api | Yes
Logging and Exception handling | Yes

## 05-07-2022
Action | Status
Has to complete Dashboard within Tuesday | Yes
Asked to fill the Revised Plan | Yes
Summary

## 06-07-2022
Action | Status
EDIT pages in department,designation,Employee | Yes
Complete the Functionality | Inprogress
Edit to update & Add to Edit slight change in ADD awards screen | Yes
change text boxes to Multiline textboxes | Yes
Summary
Rafi asked us to complete the screens fully
Var char max = can hold upto 2gb

## 07-07-2022
Action | Status
Font changes in login screen
Login Validations
Complete the validations and testing and refactoring within this week
All the validations
Summary
Rafi asked us to complete the screens fully
Var char max = can hold upto 2gb

## 08-07-2022
Action | Status
Add employee-Toastr message | Completed
Rejection reason-Toastr message | Completed
card size-make it small(min 8 cards) | InProgress
comments notification for user | InProgress
Summary
Rafi asked us to complete the functionality

## 11-07-2022
Action | Status
Add Pagination in home page | Completed | Summary
Rafi asked us to complete the functionality
Side bar image and profile image should be same | Completed
Dropdown blank problem | Completed
Dashboard | In-progress
sonarqube | In-progress
Jmeter | In-progress