## 11-04-2022
MOM | Status
In Public Home Page use "Filter" naming conversion instead of "Sort" | Yes
Avoid Scroll down pages just you can use paging | Yes
Use "Awardee" instead of "Nominee" - Naming Conversions | Yes
Select Name from the designation selection Instead of typing Employee name | Yes
Need flow for viewing the rejection Reason given by Approver in Approver's Page | Yes
Change filter's functionality in dashboard | In Progress
Start developing the Data Model | Yes

## 12-04-2022
MOM | Status
Remove Logo in Header | Yes
Don't Allow Public to Comment on any post in home page before login (Even don't allow the public to enter something in textbox) | Yes
Remove Forgot Password Checkbox in Forgot Password page | Yes
Correct All Alignment problem | Yes
Remove Remember Me Checkbox in Requester login page | Yes
If Requester Enter Any comment on any post it shows "me" (Avoid Requester name) and then what comment he gave | Yes
Correct the Breadcrumps in Requester's my award page
Remove Filter Retain Functionality | Yes
Remove ACE ID dropdown box in Add an request page (instead use name or username) | Yes
Remove Preview Functionality in awardee preview in requester page | Yes
rejection reason box have only close button(remove yes no ) | Yes
Remove Disable functionality in Dashboard Department filter | Yes
Use Stacked bar in dashboard | Yes
map the designation and department in data model | Yes
Remove Approver table in data model (refinment) | Yes
Start developing Physical model of data model | In Progress

## 13-04-2022
MOM | Status
Spelling corrections in wire frame | Yes
Alignments in wire frame | Yes
Removed Dropdown for Awards in Add Request | Yes
Date range filters in the dashboard | Yes
Relationship should not exist between Comment and emloyee in Data Model | Yes
change the Column name of PostId as AwardRequestId | Yes
Include the audit Fields | Yes
Changes in graph (x-axis Organisation) | No
Refine the operations in data model | Yes

## 20-04-2022
MOM | Status
Change datatype of the AddedBy, UpdatedBy Attributes in Award Request Table in DataModel | Yes
Spelling Correction - "Designation" | Yes
Operations in datamodel must contain Input and Output | Yes
Change FilterByAward(Award) into FilterByAward(Award type) | Yes
Naming convention - View Comments (plural) | Yes
Don't use remove functionality , instead use disable functionality | Yes
Analyse the differece between GetAwardRequest and ViewPost | Yes
Add Login and Logout operations in datamodel | Yes

## 21-04-2022
MOM | Status
Need one more Attribute in both Organisation and Department entity (Operation for getting list of departments under one specific organisation) | Yes
Multiple filters simultaneously | No
GetByStatus , PostView redundancy | Yes
Naming convention - Award Request become Award and Award becomes Award Type | Yes
Write operation in Status Entity | Yes
Need Designation ID, Department ID, ACE ID in Employee Entity | Yes
Logout's input and output method
Pass objects instead of IDs | Yes

## 22-04-2022
MOM | Status
Remove Period Parameter instead use fromdate - todate | Yes
Naming convention - Use "GetAwardByStatus" from "GetByStatus" in Award Entity | Yes
GetMyAward(Status) - include paramenters what is required | Yes
Need Cross cutting layer in System Architecture | Yes
Keep Organisation, Department, Designation as a separate service | Yes
Interaction diagram should contain all relevant services | Yes