## Sheet1
S.No | Task | Sub Tasks | Estimation in Hrs
1 | Login | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5 | 10
|  | Service Validations , Exception and Logging | 1.5
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 1
2 | Forgot Password | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 1
|  | HTML Validations | 0.5 | 7
|  | Web API - Service Implementation | 0.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 0.5
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
Code Merging
Integration Testing
Compatibility testing
3 | Home Page | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 3
|  | HTML Validations | 2
|  | Web API - Service Implementation | 4 | 24
|  | Web API Integration | 4
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2
4 | My Awards | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1 | 17
|  | Web API - Service Implementation | 3
|  | Web API Integration | 3
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
Code Merging
Integration Testing
Compatibility testing
5 | Profile | Low Level Design - Sequence Diagram | 0.5
|  | HTML preparation | 1
HTML Validations
|  | Web API - Service Implementation | 1 | 8
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1.5
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1
6 | Awards Dashboard | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 4 | 36.5
|  | HTML Validations | 2
|  | Web API - Service Implementation | 10
|  | Web API Integration | 10
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2.5
Code Merging
Integration Testing
Compatibility testing
7 | Admin Dashboard | Low Level Design - Sequence Diagram | 4
|  | HTML preparation | 4
|  | HTML Validations | 1.5
|  | Web API - Service Implementation | 10
|  | Web API Integration | 10 | 38
|  | Swagger - API Documentation | 2
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 2.5
8 | Admin -List Awards | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 0.2
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1 | 9.2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
Code Merging
Integration Testing
Compatibility testing
9 | Admin -Add Awards | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2 | 13.5
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 1
10 | Admin -View Awards | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
HTML Validations
|  | Web API - Service Implementation | 0.5
|  | Web API Integration | 0.5 | 8
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Code Merging
Integration Testing
Compatibility testing
11 | Admin -Edit Awards | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1 | 9.5
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 0.5
12 | Admin -Disable Awards | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1 | 8.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Code Merging
Integration Testing
Compatibility testing
13 | Admin -List Employees | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 0.2
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1 | 9.2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
14 | Admin -Add Employee | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 2 | 13.5
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 1
Code Merging
Integration Testing
Compatibility testing
15 | Admin - View Employee | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
HTML Validations
|  | Web API - Service Implementation | 0.5
|  | Web API Integration | 0.5
|  | Swagger - API Documentation | 1 | 8
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
16 | Admin - Edit Employee | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API - Service Implementation | 1
|  | Web API Integration | 1 | 9.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 0.5
Code Merging
Integration Testing
Compatibility testing
17 | Admin - Disable Employee | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 5
|  | Web API Integration | 5
|  | Swagger - API Documentation | 1 | 21.5
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
18 | Admin -List Organisations | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 2 | 15
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
Code Merging
Integration Testing
Compatibility testing
19 | Admin - Add Organisation | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 4 | 19.5
|  | Web API Integration | 4
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
20 | Admin - Edit Organisation | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API - Service Implementation | 1 | 9.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 1
|  | Code Review | 1
|  | Unit Testing | 0.5
Code Merging
Integration Testing
Compatibility testing
21 | Admin - Disable Organisation | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 5
|  | Web API Integration | 5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5 | 21.5
|  | Code Review | 1
|  | Unit Testing | 2
22 | Admin - List Departments | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1 | 15
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
Code Merging
Integration Testing
Compatibility testing
23 | Admin - Add Department | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 4
|  | Web API Integration | 4
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1 | 19.5
|  | Unit Testing | 2
24 | Admin - Edit Department | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 4
|  | Web API Integration | 4
|  | Swagger - API Documentation | 1 | 19.5
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
Code Merging
Integration Testing
Compatibility testing
25 | Admin - Disable Department | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1 | 21.5
|  | Web API - Service Implementation | 5
|  | Web API Integration | 5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
26 | Admin - List Designations | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1 | 17
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 2
Code Merging
Integration Testing
Compatibility testing
27 | Admin - Add Designation | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 4
|  | Web API Integration | 4 | 19.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
28 | Admin - Edit Designation | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 4
|  | Web API Integration | 4 | 19.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
29 | Admin - Disable Designation | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 5
|  | Web API Integration | 5 | 21.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 2
Code Merging
Integration Testing
Compatibility testing
30 | Requester - Request List | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1.5
|  | Web API Integration | 1 | 10
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 1
31 | Requester - Add Request | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1
|  | HTML Validations | 1
|  | Web API - Service Implementation | 1.5 | 10.5
|  | Web API Integration | 1.5
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 1
32 | Requester - view Request | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
|  | HTML Validations | 0
|  | Web API - Service Implementation | 0.5
|  | Web API Integration | 0.5
|  | Swagger - API Documentation | 1 | 8
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
Code Merging
Integration Testing
Compatibility testing
33 | Approver - Approval Request List | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 0.5
|  | Web API - Service Implementation | 1.5
|  | Web API Integration | 1
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 0.5
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 1 | 10
34 | Approver - View Approval Request | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 1.5
|  | HTML Validations | 0
|  | Web API - Service Implementation | 0.5
|  | Web API Integration | 0.5
|  | Swagger - API Documentation | 1 | 8
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 0.5
35 | Approver - Accept / Reject | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2 | 16
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1.5
|  | Code Review | 1
|  | Unit Testing | 2
36 | Approver - Reject Reason | Low Level Design - Sequence Diagram | 1.5
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 2 | 16
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 1.5
|  | Code Review | 1
|  | Unit Testing | 2
Code Merging
Integration Testing
Compatibility testing
37 | Publisher - Publish Request List | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1 | 13
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 1.5
38 | Publisher - View Publish Request | Low Level Design - Sequence Diagram | 1
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2 | 12.5
|  | Web API Integration | 2
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 1
|  | Code Cleanup | 0.5
|  | Code Review | 0.5
|  | Unit Testing | 1.5
39 | Publisher - Publish | Low Level Design - Sequence Diagram | 2
|  | HTML preparation | 2
|  | HTML Validations | 1
|  | Web API - Service Implementation | 2
|  | Web API Integration | 2 | 15
|  | Swagger - API Documentation | 1
|  | Service Validations , Exception and Logging | 2
|  | Code Cleanup | 0.5
|  | Code Review | 1
|  | Unit Testing | 1.5
|  | ESTIMATED TIME | 586.4
|  | BUFFER HOURS | 20
|  | TOTAL | 606.4