## 05-04-2022
Resource Name | Action Point / Impediments | Status | Comments
Archana M
Aravinth S
Atsaya A | System issue | informed to admin team
Vidhya Priya
Karthickraja S | No system available | informed to admin team
Aakaash M | System issue | informed to admin team
Jeevanandham | No system available | informed to admin team
Ajaybharathi | No system available | informed to admin team
Logesh
Madujith M A
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Aakaash M | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Ajaybharathi K | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Aravinth S | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Archana M | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Atsaya A | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Jeevanantham N | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Karthickraja S | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Logesh Kumar K | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
Madujith M A | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1
VidhyaPriya V | 1.modifying user story,flow diagram. 2.session with rafi - abstract factory pattern.3.meeting with rafi-about project user story.4.entity framework(code first approach).5.discussion about the meeting | made a user flow diagram and user story | NIL | 4,1,0.5 | 1,1

## 06-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | 1.Discussion about wire frame. 2.Designing wire frame for the Requester and Approver | 1.Drilled down the User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Discussion about the meeting. | wire framing for the UI of HR Page | 1,1,3,0.5,0.5 | 1
Ajaybharathi K | 1.Acceptance criteria 2.Constraints 3.Dependencies 4.assumptions | 1.Prepare a Flowchart for User Stories. 2.Meeting with Rafi. 3.Discussion about the meeting. | NIL | 4,1,0.5 | 1,1
Aravinth S | 1. wireframe for approver 2.Constraints 3.Dependencies | 1.Drilled down the User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Discussion about the meeting. | NIL | 3,1,0.5 | 1
Archana M | 1.discussion about wire frame . 2.made wire frame on Admin home page(manage employee,manage Award,manage Department). | 1.Meeting with rafi. 2.drilled down the user story. 3.Discussion about the meeting . 4.rework on flow diagram | wire framing for the UI of Admin | 1,1,3,0.5,0.5 | 1
Aakaash M | 1. Wire framing for the UI of Public pages. 2. Removed duplicates from the User Stories. | 1.Drilled down the User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Project Review. 5.Discussion about the meeting. | Wire framing for the UI of Dashboard | 2 - 1 - 1 | - 1 - 2 -
Jeevanantham N | 1.Acceptance criteria 2.Constraints 3.Dependencies 4.assumptions | 1.Prepare a Flowchart for User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Discussion about the meeting. | NIL | 4,1,0.5 | 1,1
Karthickraja S | 1.Discussion about wire frame. 2.Designing wire frame for the Requester and Approver | 1.Meeting with rafi. 2.drilled down the user story. 3.Discussion about the meeting . 4.rework on flow diagram | wire framing for the UI of HR Page | 1,1,3,0.5,0.5 | 1,1
Logesh Kumar K | 1. Designing wireframe for approver 2.Constraints | 1.Drilled down the User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Discussion about the meeting. | NIL | 3,1,0.5 | 1,1
Madujith M A | 1.Discussion about wire frame,2.Designing wire frame for the home page | 1.Drilled down the User Stories. 2.Exploration on Abstract factory pattern. 3.Meeting with Rafi. 4.Discussion about the meeting. | NIL | 2 - 1 1 | - 2 - -
VidhyaPriya V | 1.Wireframe for Admin 2. | 1.Meeting with rafi. 2.drilled down the user story. 3.Discussion about the meeting . 4.rework on flow diagram | wire framing for the UI of Admin | 1,1,3,0.5,0.5 | 1,1
| Resource Name | Action Point / Impediments | Status | Comments
Archana M
Aravinth S
| Atsaya A | System issue | informed to admin team
VidhyaPriya V
| Karthickraja S | No system available | Informed to admin team
| Aakaash M | System issue | informed to admin team
| Jeevanantham N | No system available | informed to admin team
| Ajaybharathi | No system available | informed to admin team
Logesh
| Madujith M A | Pulling from Git and again uploading it to One drive inorder to edit Excel Sheet and again downloading from one drive and pushing back to the scm(GIT) seems to be a tedious process |  | Need access for excell desktop version

## 07-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | 1.Discussion on prototype. 2.Reworking on wire frame for the Requester (Award page,my request page)and Approver(Award page,my request page,approver page)AND HR page | 1.Meeting with rafi(wire frame) 2.Session on Abstract Factory Pattern. 3.rework on prototype | NIL | 0.5,5.5,1 | 1
Ajaybharathi K | 1. Acceptance criteria. 2.Dependencies. 3.Assumptions. | 1.Explored on git - How to clone, push ,pull . 2.Created acceptance criteria for all user stories. 3.Created assumptions for public user story. 4.Session on Abstract factory design pattern. 5.Meeting with Rafi. | NIL | 1-2-2-1 | 1
Aravinth S | 1. designing wireframe for dashboard 2.Constraints | 1. designed wireframe for approver 2. Explor about constraints 3.meeting with rafi (MOM) | NIL | 4,1,1 | 1
Archana M | 1.Discussion on prototype. 2.Reworking on wire frame for the Admin (Manage employee,manage Award,Manage Orz) | 1.Meeting with rafi(wire frame) 2.Session on Abstract Factory Pattern. 3.rework on prototype(ADMIN) | NIL | 0.5,5.5,1 | 1
Aakaash M | Redesigning the home page, Dashboard in Admin page | 1)Designed Wireframe for the Public and Approver pages 2)Discussion about redesigning the wireframe 3)Session about design pattern (abstract factory) | Wire framing for the UI of HR page | 4 1 | - - 2
Jeevanantham N | 1.Acceptance criteria 2.Dependencies 3.Assumptions | 1.Explored on git - How to clone, push ,pull . 2.Created acceptance criteria for all user stories. 3.Created assumptions for public user story. 4.Session on Abstract factory design pattern. 5.Meeting with Rafi. | NIL | 1-2-2-1 | 1
Karthickraja S | 1.Discussion on prototype. 2.Reworking on wire frame for the Requester (Award page,my request page)and Approver(Award page,my request page,approver page)AND HR page | 1.Meeting with rafi(wire frame) 2.Session on Abstract Factory Pattern. 3.rework on prototype | NIL | 0.5,5.5,1 | 1
Logesh Kumar K | 1. Designing wireframe for dashboard 2.Constraints | 1. designed wireframe for approver 2. Explor about constraints 3.Explore about prototype design pattern | NIL | 4,1,1 | 2
Madujith M A | Redesinging the Home page wireframe | 1).Designed homepage wireframe. 2)Explored about Prototype design pattern.3)Disscussion meeting about redesigning the wireframe 4) Dessign pattern session( abstract factory) | NIL | 3 - 1 | - 2 - 1
VidhyaPriya V | 1.Discussion on prototype. 2.Reworking on wire frame for the Admin (Manage employee,manage Award,Manage Orz) | 1.Meeting with rafi(wire frame) 2.Session on Abstract Factory Pattern. 3.rework on prototype(ADMIN) | NIL | 0.5,5.5,1 | 1

## 08-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | 1.Reworked on Wireframe for Approver 2.Discussion About Meeting with Team 3.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Session on DesignPattern - Builder,Prototype. 3.Rework on prototype(Approver) | NIL | 2-2-1-2 | 1
Ajaybharathi K | 1.Wireframe For HR 2.Design Admin Dashboard. | 1. Assumptions for Public 2. Git Explore 3. Session on Design Pattern - Builder, Prototype 4. Meeting with Rafi(MOM) 5. Discussion About the Meeting with Team. | NIL | 1-2-2-1 | 1
Aravinth S | 1. designing wireframe for dashboard 2.Constraints | 1. designed wireframe for approver 2. Explor about constraints 3.meeting with rafi (MOM) | NIL | 4,1,1 | 1
Archana M | 1.Reworked on Wireframe for Admin(Manage employee,Manage Award,Manage Orz) 2.Discussion About Meeting with Team 3.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Session on DesignPattern - Builder,Prototype. 3.Rework on prototype(Admin) | NIL | 2-2-1-2 | 1
Aakaash M | Improving the wireframe with neat flow | 1)Designed wireframe of homepage and Login screen for each users. 2)Session about Prototype design pattern. 3)Disscussion meeting about Wire Frame 4)Discussion meeting about redesigning the wireframe and spliting the work between teams | Nil | 4 - 1 1 | - 1
Jeevanantham N | 1.Wireframe For HR 2.Design Admin Dashboard | 1. Assumptions for Public 2. Git Explore 3. Session on Design Pattern - Builder, Prototype 4. Meeting with Rafi(MOM) 5. Discussion About the Meeting with Team. | NIL | 1-2-1-1-1 | 1
Karthickraja S | 1.Reworked on Wireframe for Requester. 2.Discussion About Meeting with Team. 3.Rechecked All Wireframes. | 1.Meeting with rafi(wire frame) 2.Session on DesignPattern - Builder,Prototype. 3.Rework on prototype(requester) | NIL | 2-2-1-2 | 1
Logesh Kumar K | 1. Designing wireframe for dashboard 2.Constraints | 1. designed wireframe for approver 2. Explor about constraints 3.Explore about prototype design pattern | NIL | 4,1,1 | 2
Madujith M A | Redesinging the Home page wireframe, Desiging poster for the published award | 1).Designed homepage and sidebar wireframe. 2)Session about Prototype design pattern.3)Review meeting with Rafi about redesigning the wireframe 4) discussion meeting about redesigning the wireframe and spliting the work between teams | NIL | 4 - 1 - | - 1 - 1
VidhyaPriya V | 1.Reworked on Wireframe for Admin(Manage employee,Manage Award,Manage Orz) 2.Discussion About Meeting with Team 3.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Session on DesignPattern - Builder,Prototype. 3.Rework on prototype(Admin) | NIL | 2-2-1-2 | 1

## 09-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | 1.Reworked on Wireframe for Requester(award,request,profile) and approver (award,approve,request,profile). 2.Discussion About Meeting with Team. 3.Rechecked All Wireframes. | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Approver) | NIL | 4-0.5-1-1.5-2 | -
Ajaybharathi K | 1.Wireframe For HR 2.Rechecked Admin ManageOrganization | 1. Wireframe for HR 2. Recheck on Wireframe Approver Requester 3. Meeting with Rafi(MOM) 4. Discussion About the Meeting with Team. | NIL | 3-1-2-1 | 1
Aravinth S | 1. Redesigning wireframe for dashboard | 1. designed wireframe for Dashboard 2.meeting with rafi (MOM) | NIL | 4,2 | NIL
Archana M | 1.Reworked on Wireframe for Admin(Home page,Manage employee,Awards,Organization,Department) 2.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Admin)3.Discussion about Meeting with team(Wireframe) | NIL | 2,1,2,2,1 | -
Aakaash M | Developing the workflow of the homepage wireframe and desgining the login workflow | 1)Brain Storming with team for - 1 hour. 2).Refining the Home page and lading page wireframes - 2 hours | Nil | 3 hrs | -
Jeevanantham N | 1.Wireframe For HR 2.Rechecked Admin Manage Employee | 1. Wireframe for HR 2. Recheck on Wireframe Approver Requester 3. Meeting with Rafi(MOM) 4. Discussion About the Meeting with Team. | NIL | 3-1-2-1 | 1
Karthickraja S | 1.Reworked on Wireframe for Requester(award,request,profile) and approver (award,approve,request,profile). 2.Discussion About Meeting with Team. 3.Rechecked All Wireframes. | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Requester) | NIL | 4-0.5-1-1.5-2 | -
Logesh Kumar K | 1. Redesigning wireframe for dashboard | 1. designed wireframe for Dashboard 2.meeting with rafi (MOM) | NIL | 4,2 | NIL
Madujith M A | Developing the workflow of the homepage wireframe and desgining the login workflow | 1)Brain Storming with team 2).Refining the Home page and landing page wireframes 3) discussion meeting about redesigning the wireframe and spliting the work between teams | NIL | 1 4 1 | -
VidhyaPriya V | 1.Reworked on Wireframe for Admin(Home page,Manage employee,Awards,Organization,Department) 2.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Admin) 3.Project review 4.Discussion about Meeting with team(Wireframe) | NIL | 4,2,2,2,1,1 | 1
| Resource Name | Action Point / Impediments | Status | Comments
Archana M
Aravinth S
| Atsaya A | System issue | informed to admin team
VidhyaPriya V
| Karthickraja S | No system available | Informed to admin team
| Aakaash M | System issue | informed to admin team
| Jeevanantham N | No system available | informed to admin team
| Ajaybharathi | No system available | informed to admin team
| Logesh | No system available | informed to admin team
| Madujith M A | Pulling from Git and again uploading it to One drive inorder to edit Excel Sheet and again downloading from one drive and pushing back to the scm(GIT) seems to be a tedious process |  | Need access for excell desktop version

## 11-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | 1.Reworked on Wireframe for Requester(award,request,profile) and approver (award,approve,request,profile). 2.Discussion About Meeting with Team. 3.Rechecked All Wireframes. | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Approver) | NIL | 4-0.5-1-1.5-2 | -
Ajaybharathi K | 1.Wireframe For HR 2.Rechecked Admin ManageOrganization | 1. Wireframe for HR 2. Recheck on Wireframe Approver Requester 3. Meeting with Rafi(MOM) 4. Discussion About the Meeting with Team. | NIL | 3-1-2-1 | 1
Aravinth S | 1. Redesigning wireframe for dashboard | 1. designed wireframe for Dashboard 2.meeting with rafi (MOM) | NIL | 4,2 | NIL
Archana M | 1.Reworked on Wireframe for Admin(Home page,Manage employee,Awards,Organization,Department) 2.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Admin)3.Discussion about Meeting with team(Wireframe) | NIL | 2,1,2,2,1 | -
Aakaash M | Developing the workflow of the homepage wireframe and desgining the login workflow | 1)Brain Storming with team for - 1 hour. 2).Refining the Home page and lading page wireframes - 2 hours | Nil | 3 hrs | -
Jeevanantham N | 1.Wireframe For HR 2.Rechecked Admin Manage Employee | 1. Wireframe for HR 2. Recheck on Wireframe Approver Requester 3. Meeting with Rafi(MOM) 4. Discussion About the Meeting with Team. | NIL | 3-1-2-1 | 1
Karthickraja S | 1.Reworked on Wireframe for Requester(award,request,profile) and approver (award,approve,request,profile). 2.Discussion About Meeting with Team. 3.Rechecked All Wireframes. | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Requester) | NIL | 4-0.5-1-1.5-2 | -
Logesh Kumar K | 1. Redesigning wireframe for dashboard | 1. designed wireframe for Dashboard 2.meeting with rafi (MOM) | NIL | 4,2 | NIL
Madujith M A | Developing the workflow of the homepage wireframe and desgining the login workflow | 1)Brain Storming with team 2).Refining the Home page and landing page wireframes 3) discussion meeting about redesigning the wireframe and spliting the work between teams | NIL | 1 4 1 | -
VidhyaPriya V | 1.Reworked on Wireframe for Admin(Home page,Manage employee,Awards,Organization,Department) 2.Rechecked All Wireframes | 1.Meeting with rafi(wire frame) 2.Rework on prototype(Admin) 3.Project review 4.Discussion about Meeting with team(Wireframe) | NIL | 4,2,2,2,1,1 | 1
| Resource Name | Action Point / Impediments | Status | Comments
Archana M
Aravinth S
| Atsaya A | System issue | informed to admin team
VidhyaPriya V
| Karthickraja S | No system available | Informed to admin team
| Aakaash M | System issue | informed to admin team
| Jeevanantham N | No system available | informed to admin team
| Ajaybharathi | No system available | informed to admin team
| Logesh | No system available | informed to admin team
| Madujith M A | Pulling from Git and again uploading it to One drive inorder to edit Excel Sheet and again downloading from one drive and pushing back to the scm(GIT) seems to be a tedious process |  | Need access for excell desktop version

## 12-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | Data Model | Discussion with team. | NIL | 1 hr 15 mins | -
| Rechecked all WireFrame | wireframe for approver(changed naming conventions,flow for rejection reason) |  | 1 hr
|  | check on wireframe for HR |  | 1 hr 30 mins
|  | checked wireframe for admin(refined flow for awards,employee,department) |  | 1 hr 30 mins
Ajaybharathi K | Data Model Table | Discussion with Team | NIL | 1hr 15 mins
|  | Data Model 1st Version |  | 3 hrs
1 hr
Aravinth S | Data Model Table | entering MOM For Last 2 days | NIL | 1/2 hr
|  | Meeting with team regarding wireframe (Approver) |  |  | 1/2 hr
| Reviewing Data model | Anitha Session |  | 1/2 hr
Reviewing the Flow of the Wireframe (All)
Archana M | Rechecked all WireFrame | Discussion with team. | NIL | 1 hr 15 min
|  | Rechecked wireframe for admin(refined flow for awards,employee,department) |  | 1.5
|  | MVC Application Review |  |  | 1.5
|  | Session with Anitha |  |  | 0.5
Aakaash M | Data Models - Relationship | Entity and Operations for data model - 2hrs
Had a discussion with team - 1.15hrs
|  | Gone through the wire frames - 1hrs | NIL | 4.5hrs
Jeevanantham N | Redesign Dashboard | Discussion with Team |  | 1 hrs
|  | Rechecked for Approver, Admin Flow |  | 2
|  | Session with Anitha |  | 1
|  | Data Model |  | 1
Karthickraja S | Data Model | Discussion with team. | NIL | 1 hr 15 mins
| Rechecked all WireFrame | wireframe for approver(changed naming conventions,flow for rejection reason) |  | 1 hr
|  | check on wireframe for HR |  | 1 hr 30 mins
|  | checked wireframe for admin(refined flow for awards,employee,organisation,department) |  | 1 hr 30 mins
Logesh Kumar K |  |  | NIL
| Data model Review | Discussion with Team |  | 1hr 15 mins
| Data Model Table | Review the flow for all wireframes. |  | 1 hr
Madujith M A |  | 2 hr redesigning the DashboardDiscussion with team. |  | 1 hour 15 mins
| Dashboard redesign | redesigning the Dashboard |  | 3 hours
|  | project presentation |  |  | 1 hour
VidhyaPriya V |  |  | NIL
| NIL | Discussion with Team |  | 1 hour | NIL

## 13-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A | sample data for data model(excel sheet) | Discussion with team. | NIL | 30mins | -
|  | wireframe for approver(changed naming conventions,Add request) |  | 1 hr
|  | refined the user story |  | 1hr30mins
|  | College review |  | 30mins
|  | Meeting with Rafi( About Lesson,data model.physical model,view model ) |  | 1 hr 15 mins
|  | checked wireframe for admin(refined flow for awards,employee,department) |  | 1 hr
Ajaybharathi K | Data Model Table | Discussion with Team | NIL | 30 mins
|  | Normalisation |  | 1 hr
|  | Physical Data Model |  | 2hr 30mins
|  | Meeting with Rafi( plan for next 3days ) |  | 1hr
Aravinth S |  | entering MOM For Last day | NIL | 1/2 hr
|  | Logo removed for all wireframe pages some alignment corrections |  | 1/2 hr
|  | Session about lesson learned (planning for 4 days - Services, Operations, class diagram, view model) |  |  | 1 hr
| Refining Constraints, dependencies for each user story |  |  | 2 hr
Archana M |  | Discussion with team. | NIL | 30mins
| Normalization | Rechecked wireframe for admin(refined flow for awards,employee,department) |  | 1hr30mins
|  | refined the user story |  | 1hr30mins
|  | Meeting with Rafi( About Lesson,data model.physical model,view model ) |  |  | 1hr15mins
Aakaash M | Dashboard modiications | Rechecked the Prototype with the last MOM - 1hr | NIL | 3.5hrs | 15mins
Had a discussion with team - 1.15hrs
Discussed and implemented the Physical model - 1hrs
Jeevanantham N | Redesign Dashboard | Discussion with Team |  | 30mins
|  | Project Review Preparation |  | 2 hr
|  | Normalisation |  | 1 hr
|  | Project Review |  | 40 min
|  | Checked Admin flow |  | 1 hr
Karthickraja S | sample data for data model(excel sheet) | Discussion with team. | NIL | 30mins | -
|  | wireframe for requester(Add Request) |  | 30min
|  | rechecked wireframe for approver(Add Request,changed naming conventions) |  | 1 hr
|  | wireframe for HR(Add Request) |  | 1 hr
|  | Meeting with Rafi( About Lesson,data model.physical model,view model ) |  | 1.15min
|  | rechecked wireframe for admin(refined flow for awards,employee,organisation,department) |  | 1 hr 30 mins
Logesh Kumar K |  |  | NIL
|  | Learned normalization concepts |  | 1 hr
| Refining use cases(dependencies,constraints) | Discussion with team. |  | 30 mins
|  | Session with Rafi about Lessions learned in project training and what to do for next 7 days |  |  | 1 hr
Madujith M A |  | Discussion with team. |  | 1 hour 15 mins
| Dashboard redesign | redesigning the Dashboard |  | 3 hours
|  | Session with Rafi regarding lessons learned and what we are going to do till next mid week |  |  | 1 hour
VidhyaPriya V |  | Discussion with team. | NIL | 30mins
|  | Rechecked wireframe for admin(refined flow for awards,employee,department) |  | 1hr30mins
| Normalization | Refined the user story |  | 1hr30mins
|  | Meeting with Rafi( About Lesson,data model,physical model,view model ) |  |  | 1hr15mins

## 16-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  |  | NIL | - | -
| Absent | Absent
Ajaybharathi K |  |  | NIL
|  | Reworked on DataModelling |  | 2hours
Aravinth S |  |  | NIL
|  | recap about Exception handling in C# |  | - | 1 hr
| Entity Framework |  |  |  | 1 hr
Archana M |  |  | NIL
| Angular |  |  | 2hr
|  | Explored C# |  |  | 2hr
Aakaash M |  |  | NIL | 3.5hrs | 1
| HLD, Angular | Worked on dashboard - Features - 3hrs
Explored about implementing Graph - 1hr
Jeevanantham N |  |  | NIl
| HLD | C# Explore |  | 1hr | 4hr
What is Web API ?
Karthickraja S |  | created home page (HTML,CSS,BOOTSTRAP) | NIL | 3.5HRS
Logesh Kumar K |  |  | NIL
| Entity Framework | Explore about HLD |  | 2hr | 1hr
| Angular |  |  |  | 1 hr
Madujith M A
|  | redesigning the Dashboard with date filter,altering the fields(x-axis) |  | 3 hours
|  | Exploration about angular and dashboard integration using angular |  |  | 1 hour
VidhyaPriya V |  |  | NIL
|  | refined the Datamodel |  | 2 hours | 2 hours
Angular

## 18-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  |  | NIL | - | -
| Absent | Absent
Ajaybharathi K |  | Discussion with Team about HLD | NIL | 1hour
|  | Data Dictionaries And View model in HLD |  | 2 hour
|  | Modules and Features in HLD |  | 30 mins
Aravinth S |  |  | NIL
| Absent | absent |  | - | -
Archana M |  | Discussion with team about HLD | NIL | 1
|  | working on Award home page (HTML) |  | 4hr
|  | Discussion with team. |  | 1hr
| Angular |  |  |  | 1hr15mins
Aakaash M |  | Discussion with Team - 1.30hrs | NIL | 4.5hrs | 1
| HLD, Angular | Worked on HLD - Features - 3hrs
Explored and collected information on Facade design pattern - 1hr
Jeevanantham N | HLD | Discussion with Team about HLD | NIl | 2hr30mins
| Angular | C# Access Modifiers with Examples |  | 1hr | 40mins
| Web API | Web API Sample Project Understanding |  | 2hr30mins
Karthickraja S | Angular | Discussion with team about HLD | NIL | 1hr | 1hr
|  | working on Award home page (HTML) |  | 4 hrs
|  | Discussion with team. |  | 1hr
Logesh Kumar K |  |  | NIL
| Absent | Absent |  | -
Madujith M A |  | Discussion with team. |  | 1 hour
|  | Worked on HLD - Features |  | 3 hours
|  | Exploration in angular |  |  | 1 hour
VidhyaPriya V |  | Discussion with team about HLD | NIL | 1 hour
|  | Modules and Features in HLD |  | 1 hour
| Angular | View Model in HLD |  | 1 hour | 1hour
| HLD |  |  |  | 1 hour

## 19-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  |  | NIL | - | -
| Absent | Absent
Ajaybharathi K |  | Standup Meeting | NIL | 30mins
| Web API | Explored on how to create Webapi |  | 30 minutes
|  | Explored on Typescript |  | 30 minutes
| System Architecture in HLD |  |  | 1hour
| Services in HLD |  |  | 1hour
Aravinth S |  | Standup Meeting | NIL | 30mins
| EF | Discussion with team about Yesterday (18-04-2022) activities (HLD) |  | 30 minutes | 2 hr
| Typescript | Typescript sample program Assignment |  |  | 30 mins
Archana M | Typescript (sample program) | Standup Meeting | NIL | 30mins | 1hr
|  | Recollected the basic concepts(oops,datatype,sql,access modifiers,constructor) |  | 3.5 hrs
|  | Discussion about services |  | 30mins
Aakaash M |  | Standup Meeting - 1hr | NIL | 4.5hrs | 1
| HLD, HTML Layouts | Explored Type Script - 1.5hrs
HTML layout for Login page - 2hrs
Jeevanantham N |  | Standup Meeting | NIl | 30mins
|  | Review the Features and Modules |  | 1hr
|  | Typescript (sample program) |  |  | 1hr
| Web API |  |  |  | 2hr
Karthickraja S |  | Standup Meeting | NIL | 30mins | 1hr
| Typescript (sample program) | Recollected the basic concepts(oops,datatype,sql,access modifiers,constructor) |  | 3.5 hrs
|  | Discussion about services |  | 30mins
Logesh Kumar K |  |  | NIL
|  | Standup meeting about HLD |  | 30 mins
| Typescript | Write the typescript sample program |  | 30 mins | 1 hr
|  | Explore about angular |  |  | 1 hr
Madujith M A |  | Standup Meeting |  | 30mins
|  | Exploration about Type script |  | 3 hours
|  | Exploration about angular and dashboard integration using angular |  |  | 1 hour
VidhyaPriya V |  | Standup Meeting | NIL | 30mins
|  | Explored on Web API |  | 1 hour
| Angular | Done Typescript sample program |  | 1 hour | 1hour
| HLD |  |  |  | 1 hour

## 20-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  |  | NIL | - | -
| Absent | Absent
Ajaybharathi K |  | Standup Meeting | NIL | 30mins
| HLD | Softskills |  | 1hour
|  | Session with Rafi about Web API, Html layout, HLD. |  | 45 mins
Aravinth S |  | Standup Meeting with team about HLD | NIL | 30mins
| recap the Web API, EF | Softskills session |  | 1 hr | 30 mins
| Typescript | Session with Rafi about the work plan for this week (Web API, Html layout, HLD) |  | 45 mins | 1 hr
Archana M |  | Standup Meeting | NIL | 30mins | 1hr
Referred the HLD Document
|  | Soft skill session with Jaya |  | 1 hr
|  | Completed MOM |  | 20mins
|  | Session with Rafi Work plan for upcoming days(HLD,HTML layouts as per prototype) |  | 45mins
Aakaash M |  | Standup Meeting | NIL | 4.5hrs | 1
| HTML layouts | Softskill session - 1hr
HTML layout for Login and forgot password screen
Jeevanantham N |  | Standup Meeting | NIl | 30mins
|  | Review the Features and Modules |  | 1hr
|  | Typescript (sample program) |  |  | 1hr
| Web API |  |  |  | 2hr
Karthickraja S |  | Standup Meeting | NIL | 30mins | 1hr
|  | Referred the HLD Document |  | 1 hr
|  | Soft skill session with Jaya |  | 1 hr
|  | Completed MOM |  | 20mins
|  | Session with Rafi Work plan for upcoming days(HLD,HTML layouts as per prototype) |  | 45mins
Logesh Kumar K |  | Standup meeting about HLD | NIL | 30 mins
|  | Softskills session |  |  | 1 hr
| Web API | Explore HLD about dependency, layers,third party integration |  | 2 hr
|  | Session with Rafi about the work plan for this week (Web API, Html layout, HLD) |  | 45 mins
Madujith M A |  | Standup Meeting | NIL | 30mins
|  | Exploration about Type script |  | 3 hours
|  | Softskill session |  |  | 1 hour
|  | Session with Rafi about the work plan for this week (Web API, Html layout, HLD) |  | 45mins
VidhyaPriya V |  | Standup Meeting | NIL | 30mins
|  | Soft skill session with Jaya |  | 1 hour
| Angular | Session with Rafi on HLD and discussed workplan for this week(HLD,HTML Layout,Web API) |  | 45 mins | 1hour
| Services in HLD |  |  |  | 2 hours

## 21-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  |  | NIL | - | -
| Absent | Absent
Ajaybharathi K |  | Standup Meeting | NIL | 30mins
| HLD | Discussed on Prototype with Team |  | 1hr 30mins
|  | Worked on datamodel operations |  | 2hrs
|  | Meet Rafi for Project clarification(Status, Delete) |  | 10mins
Aravinth S |  | Standup Meeting | NIL | 30mins
| recap about Architecture pattern in ppt | Prototype review with team |  | 1 hr 30 mins
|  | DataModel Reviewed |  | 30 mins
Archana M |  | Standup Meeting | NIL | 30 mins
|  | Reviewed the prototype with team |  | 1 hr 30 mins
|  | Reviewed DataModel and services |  | 1 hr 30 mins
| HLD(NFR) |  |  |  | 1hr
Aakaash M |  | Standup Meeting - 30 mins | NIL | 3hrs
| Physical Model | Reviewed Prototype with team - 1.30hrs
Reworked on Data model - 1 hr
Jeevanantham N |  | Standup Meeting | NIl | 30mins
|  | Reviewed Prototype with team |  | 1hr30mins
| Services | Reviewed DataModel |  | 1hr
| Web API | Discussed about services |  | 2hrs | 1hr
Karthickraja S |  | Standup Meeting | NIL | 30mins
| HLD(Services) | Reviewed Prototype with team |  | 1hrs30mins
|  | Reworked on Data model |  | 2hrs
|  | Dicussed about Services |  | 30mins
|  | Meet Rafi for Project clarification(Status, Delete) |  | 10mins
Logesh Kumar K |  | Standup meeting | NIL | 30 mins
| Data Model Operations | Reviewed the prototype |  | 1 hr 30 mins
|  | College reward points Review meeting |  |  | 30 mins
Madujith M A |  | Standup Meeting | NIL | 30 mins
| Physical model | reviewing the prototype |  | 1 hour
|  | Discusssing the MOM,about the status disabling feature |  | 1hour
|  | Helping to do the datamodel |  | 1 hour
|  | meeting with rafi and doing the MOM changes(naming conventions , identify more methods) |  | 3.5v hours
VidhyaPriya V |  | Standup Meeting | NIL | 30 minutes
|  | Reviewed the complete flow of the prototype |  | 1 hours 30 minutes
| Non functional requirements | Rework on Data model |  | 1 hour | 1 hour

## 22-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  | Standup Meeting | NIL | 30 mins | -
| HTML Layout for Requester Award Page | Discussed Data model,physical model |  | 1 hr 30 mins,1hr
|  | Reworked on protype |  | 2 hrs
Ajaybharathi K |  | Standup Meeting | NIL | 30mins
|  | Worked On class diagram |  | 2hrs
| HLD | Worked on Service Interaction |  | 1hr
Aravinth S |  | Meeting with Rafi | NIL | 1 hr 45 mins
|  | Standup Meeting |  | 30 mins
| Admin HTML Home page | Explore about Sytem Architecture and System Architecture Developed (include services analyzed) |  | 1 hr | 15 mins
| EF (Basics) | DataModel Reviewed |  | 30 mins
|  | Reworked on prototype (breadcrumbs, Award type filters) |  | 2 hrs
Archana M |  | Review with Rafi(Prototype and Data Model) | NIL | 1 hr 45 mins
| HLD(Non functional requirements) | Standup Meeting |  | 30 mins
| Web API | Reviewed DataModel |  | 1 hr | 1hr 30 mins
|  | Discussed about services |  | 1 hr
Aakaash M |  | Review meeting with Rafi - 1hr 45mins | NIL | 5.15hrs
Team Meeting - 30 mins
| Physical Model | System Architecture - 1hr
Database Diagram - 2hrs
Jeevanantham N |  | Meeting with Rafi(Prototype, DataModel) | NIl | 1hr45mins
|  | Standup Meeting |  | 30mins
|  | Reviewed Physical Model, Data Model |  | 1hr30min
| Services | Discussion About Services |  | 2hrs
| Web API |  |  | 2hrs
Karthickraja S |  | Standup Meeting | NIL | 30mins
| Reworked on home page layout | Reviewed(Data model,physical model,services) |  | 1hr,1hr
|  | Reworked on prototype |  | 2hrs
|  | meeting with rafi |  | 1hr 45mins
|  | Meet Rafi for team clarification |  | 10mins
Logesh Kumar K |  | Session with rafi (Data model review) | NIL | 2 hr
|  | Correct the mistakes in data model with team |  | 1 hr
| Reviewed the system architecture, physical model | Standup meeting |  | 30 mins
|  | Checked the prototype with datamodel operations |  | 2 hr
Madujith M A |  | Standup Meeting | NIL | 30 mins
| Disabling feature for organisation , designation, department | Checking the Datamodel with prototype |  | 2 hour
|  | Checking the Entities in the physical model |  | 1hour
|  | Helping to do the html layout |  | 1 hour
VidhyaPriya V
| absent | absent

## 23-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  | Review meeting with Rafi | NIL | 1 hour | -
|  | Change of system(admin) |  | 45 mins
| HTML Layout for Requester Request Page | Standup meeting |  | 1 hour,30 mins
|  | Html and css for sidebar |  | 3 hours
Ajaybharathi K |  |  | NIL
| Absent | Absent
Aravinth S |  | Meeting with Rafi | NIL | 1 hr
|  | MOM entered |  | 15 mins
| Admin HTML Home page | Standup meeting |  | 30 mins
| recap html tags |  |  |  | 20 mins
Archana M |  | Review with Rafi(Data Model and HLD) | NIL | 1hr 15 mins
| Approver(HTML) | Standup Meeting |  | 30 mins | 2 hr
|  | Changing of system(ADMIN) |  | 45 mins | 1hr
Aakaash M |  | Review meeting with Rafi - 1hr 15mins | NIL | 4.45hrs
Team Meeting - 30 mins
| HTML Layouts | Reworked on Dependencies & Interactions -1hr
Changing of system(ADMIN)- 45 mins
Worked on dashboard layout HTML - 2hr
Jeevanantham N
| Absent | Absent |  | Absent | Absent | Absent
Karthickraja S |  | Standup Meeting | NIL | 30mins
| login page (HTML) | worked on requester award page (HTML) |  | 2hrs,10mins
|  | Changing of system(ADMIN) |  | 45 mins
|  | meeting with rafi |  | 1hr 15mins
|  | worked on home page (HTML) |  | 1hrs 30mins
Logesh Kumar K |  | Meeting with rafi about datamodel and HLD (System Architecture, Dependency ) | NIL | 1 hr 45 mins
|  | Changing of system(ADMIN) |  | 45 mins
|  | Standup meeting |  | 30 mins
| Admin's Organisation management page | Explore about html containers, layout |  | 1 hr
Madujith M A |  | Meeting with Rafi about DataModel,HLD | NIL | 1.45 hour
| HTML layout for Admin | HTML Layout Admin under adding employees |  | 2 hour
|  | Addding Css |  | 2 hour
|  | Changing of system(ADMIN) |  | 45 mins
|  | Allignment using Bootstrap |  | 1 hour
Exploring about automatic dropdown
VidhyaPriya V |  | Standup Meeting |  | 30 mins
|  | Adding html , css and bootstrap for admin page(organization) |  | 2 hours
| HTML Layout(Admin Page) | Changing of system(ADMIN) |  | 45 mins

## 25-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  | Review meeting with Rafi | NIL | 1 hour 15 mins | -
| HTML Layout for Requester Request Page(alignment,award image) | Standup meeting |  | 30 mins
|  | Explored bootstrap forms |  | 30 mins
|  | Worked for request page(label,input fields,background) |  | 2 hours
Ajaybharathi K |  | Standup meeting | NIL | 30 mins
|  | Worked on Comments in Post layout |  | 30 mins
| web api for Employee | Working on web api for Employee |  | 2 hours
Aravinth S |  | Meeting with Rafi | NIL | 1 hr 15mins
|  | MOM entered |  | 15 mins
| Requester's request page | Standup meeting |  | 30 mins
Archana M |  | Review Meeting with Rafi on HTML Layouts | NIL | 1hr 15 mins
|  | Standup Meeting |  | 30 mins
| Approver(HTML) |  |  | 2 hr
Aakaash M
| Absent | Absent
Jeevanantham N |  | Standup meeting |  | 30 mins
|  | Worked on Comments in Post layout |  | 30 mins
| web api for Employee | Working on web api for Employee |  | 2 hours
Karthickraja S |  | Standup Meeting | NIL | 30mins
| home page(post) |  |  | 2hr 30 mins
|  | explore about templets |  | 2hr
|  | Meeting with Rafi |  | 1hr 15 mins
Logesh Kumar K |  | Meeting with Rafi | NIL | 1 hr 15 mins
| Working on Admin management page | Standup meeting |  | 30 mins
|  | Explore about the Entity Framework (code first approach) |  | 30 mins
|  | Explore the layouts and bootstrap |  | 1 hr
Madujith M A |  | Standup meeting | NIL | 30 mins
| responsive HTML layout for sidebar and nav bar | Html skeleton for sidebar |  | 30min
|  | Html skeleton for nav bar |  | 30mins
|  | Adding css for the nav bar and side bar using bootstrap |  | 2 hours
|  | Aligning the elements and fixing the responsive issue of logout button |  | 1.5hours
VidhyaPriya V |  | Meeting with Rafi on HTML Layouts |  | 1 hour 15 mins
|  | Standup meeting |  | 30 minutes
| HTML Layout(Admin Page) | HTML Layout and Adding Css (Tables,Pagination) for Award,Employee,Organization,Department,Designation in Admin Page |  | 2 hours 30 minutes

## 26-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  | Review meeting with Rafi | NIL | 20 mins | -
| HTML Layout for Requester Request Page(award image) | Standup meeting |  | 30 mins
|  | Soft skill session with savitha |  | 1 hour
|  | Worked for request page |  | 2 hours 30 mins
Ajaybharathi K |  | Standup meeting | NIL | 30 mins
|  | Worked on Login Layout |  | 1 hour
| Disable layout | Softskill |  |  | 1 hour
|  | Worked on Disable Layout |  | 1 hour
Aravinth S |  | Meeting with Rafi | NIL | 30 mins
|  | MOM entered |  | 10 mins
| Requester's request page | Soft skill session with savitha |  | 1 hr
Archana M |  | Review Meeting with Rafi on HTML Layouts | NIL | 20 mins
|  | Standup Meeting |  | 30 mins
| Approver(HTML) | Soft skill session with savitha |  | 1 hr | 2hr
Aakaash M |  | 8.30-9.00 : Team Meeting
| Dashboard | 9.30 - 10.30 : Soft Skill Session on Presentation | NIL
10.45 - 1 : Html Layouts on Admin view page and dashboard
Jeevanantham N |  | Standup meeting |  | 30 mins
|  | Softskill with Savitha |  | 1 hr
| Disable Screen Employee | Worked on Login Layout |  | 1 hr
|  | Table Modification |  | 1 hr
Karthickraja S |  |  | NIL
| Absent | Absent
Logesh Kumar K |  | Review Meeting with Rafi | NIL | 20 mins
| Admin Management Page | Standup meeting |  | 30 mins
|  | Softskill session with Savitha |  | 1 hr
|  | Admin add Employee Page |  | 2 hr
Madujith M A |  |  | NIL
| responsive HTML layout for sidebar and nav bar | meeting with rafi on HTML Layouts |  | 20mins
|  | Addding icons in the side bar and aligning items |  | 2 hours 30 mins
|  | Standup meeting |  | 30mins
|  | Thinking about Css corrections to colobrate things |  | 1 hour
|  | Helping to do the css for tables, new request, |  | 1 hour
|  | exploring the MDB bootstrap |  | 2 hours
VidhyaPriya V |  | Meeting with Rafi on HTML Layouts |  | 10 minutes
|  | Standup meeting |  | 30 minutes
| Integrating the pages(admin) | Softskill with Savitha |  | 1 hour
|  | HTML Layout and Css forAdmin (List )Pages |  | 3 hours

## 27-04-2022
Resource Name | In-progress | Done | Discarded / Hold | Hours Spent - Project | Hours Spent - Non Project | Comments
Atsaya A |  | 8.30-9.00am Standup meeting |  | 30 mins
|  | 9.00-9.45am Form layout for adding request page |  | 45 mins
|  | 9.45-10.30am Soft Skill session |  | 45 mins
| Entity Realtionships,Fluent Api,Web Api | 10.55am-1pm Added container,form alignment for adding reuqest page |  | 2 hours 5 mins
|  | 1.50-2pm Timesheet update |  | 10 mins
|  | 2-2.50pm added Profile Image for adding request page |  | 50 mins
|  | 2.50-4.35pm- Meeting with rafi |  | 1 hour 45 mins
|  | 5.05-5.30 Team meeting |  | 25 mins
|  | 5.30-6.00 Entity Framework exploration |  | 30 mins
|  | 7.00pm-8.00pm Exploration on Db context ,Db Set |  | 1 hour
|  | 9.30-11pm Exploration on DBcontext operations |  | 1 hour 30 mins
Ajaybharathi K |  | Standup meeting |  | 30 mins
|  | Worked on login layout |  | 1 hour
| EF Core ,Web api | Softskill session with savitha |  |  | 45 mins
|  | Worked on Disable Layout |  | 1 hour
|  | Meeting with rafi |  | 1 hour 45 mins
|  | Discussion with team about whatever discussed in customer meeting |  | 25 mins
|  | started exploration on EF Core, WebApi |  | 45mins
Aravinth S |  | Standup meeting - 8: 30 am - 9: 00 am |  | 30 mins
|  | Working on Requester List Table - 9 : 05 am to 9 : 30 am |  | 25 mins
| Requester List table and Raise request page in new layout | Soft Skills with savitha - 9 : 45 am to 10 : 30 am |  |  | 45 mins
|  | Working on Requester List Table(changes) - 10 : 45 am to 1 : 00 pm |  | 2 hr 15 mins
|  | Review with rafi - 2 : 50 pm to 4 : 35 pm |  | 1 hr 45 mins
|  | MOM entered and responsiblity list - 4 : 55 pm to 5 : 05 pm |  | 10 mins
|  | meeting with team - 5 : 05 pm to 5 : 30 pm |  | 30 mins
|  | HTML pages list entered in Excel - 5 : 30 pm to 6 : 30 pm |  | 1 hr
|  | Layout design - 9 : 20 pm to 12 : 00 am |  | 2 hr 20 mins
Archana M |  | 8.30- 9.00 am Standup Meeting |  | 30 mins
|  | 9.00 - 9.45 Approver Layout |  | 45 mins
|  | 9.45 - 10.30 Soft skill Session |  | 45 mins
|  | 10.45 - 1.00 Approver layout with popup |  | 2 hr 15 mins
| Approver Flow | 2.00 - 2.30 Reviewed admin Layout |  | 30 mins
|  | 2.30-2.40 Time Sheet Update |  | 10 mins
|  | 2.50- 4.35 Meeting with Rafi |  | 1 hr 45 mins
|  | 5.05 - 5.30 Team Meeting |  | 25 mins
|  | 5.30 - 6.30 Approver Layout |  | 1 hr 45 mins
|  | 8.00 - 8.30 Gone through ppt (Requirements and Design) |  | 30mins
Aakaash M
|  | Review meeting Rafi - 2 : 50 pm to 4 : 35 pm |  | 1.45 mins
|  | Team Meeting - 5.05 - 5.30 |  | 25 mins
|  | Exploration on Angular - 5.30 - 6.00 |  | 30 mins
| Dashboard layout | Standup meeting - 8: 30 am - 9: 00 am |  | 30 mins
|  | Explored on chart.Js - 9.10am - 10.00am |  | 50 mins
|  | HTML Dashboard layout |  | 2hr
|  | Lunch & Break - 1hr |  | 1hr
Jeevanantham N |  | Standup meeting - 8: 30 am - 9: 00 am |  | 30 mins
|  | Softskill with Savitha |  |  | 45 mins
| Sample web api | Worked on Login Layout |  | 1hr
|  | Table Modification |  | 2hr
|  | Worked on disable layout |  | 1hr
|  | Meeting with rafi |  | 1 hour 45 mins
|  | Discussion with team about the project review meeting |  | 25 mins
|  | Explored on EF core ,sample api |  | 2 hr
Karthickraja S
|  | 9.00-11.00am Made home page layout |  | 2 hrs
| responsiveness(Homepage,more comments) | 5.00-6.00 pm Made Comment Page |  | 1hr
Logesh Kumar K |  | Standup meeting - 8: 30 am - 9: 00 am |  | 30 mins
|  | Create content for Admin Add employee - 9:00 am - 9.45 am |  | 45 mins
|  | Softskill Session - 9.45 am - 10.30 am |  | 45 mins
|  | Alignment and responsivess for Admin employee management-10.45am-12.45pm |  | 2 hrs
| Creating the common css | layout design - 1.30 pm -2.30 |  | 1 hr
|  | Meeting with Rafi - 2.50 pm -4.35pm |  | 1hr 45mins
|  | Team Discussion - 5.05 - 5.30 |  | 25 mins
|  | Review meeting with Anitha about Exception Handling 6pm - 6.15 pm |  | 15 mins
|  | Add responsive Layout - 9pm - 11 pm |  | 2 hr
Madujith M A |  | stand up meeeting |  | 30 mins
|  | worked on html layout(side bar and nav bar) |  | 45 mins
|  | soft sill session about story telling |  | 45
|  | Helping to css for table and new request |  | 1 hour
| responsive HTML layout for sidebar and nav bar | exploring bootstrap |  | 1 hour
|  | meeting with team |  | 25 mins
|  | searching for responsive layouts |  | 1 hour
|  | Exploring about window resizing using js |  | 1 hours
|  | Exploring positions in CSS |  | 1 hour
|  | Exploring Z index in CSS |  | 1 hour
VidhyaPriya V |  | 8.30 -9.00 am - standup meeting |  | 30 minutes
|  | 9.00-9.45 am - worked on Employee List Page(admin) |  | 45 minutes
|  | 9.45-10.30 am - softskill session |  | 45 minutes
|  | 10.45am -11.30am - worked on Alignments in List Pages |  | 45 minutes
|  | 11.30 am-12.15pm - Worked on action column buttons |  | 45 minutes
|  | 12.15-12.20pm - Adding Titles in butttons |  | 5 minutes
|  | 12.20-1.00 pm - worked on awards List Page(admin) |  | 40 minutes
| Alignments in the Admin List Flow page | 2.00- 2.30 - worked on Paginations |  | 30 minutes
|  | 2.30- 2.50pm - Worked on Organization,Designtion and Department Pages |  | 20 minutes
|  | 2.50-4.35pm - Meeting with Rafi |  | 45 minutes
|  | 4.50-5.05 pm - Checking Responsiveness of the Page |  | 15 minutes
|  | 5.05 - 5.30pm Team Meeting |  | 35 minutes
|  | 5.30 - 5.45 pm - rework on Layouts |  | 15 minutes
|  | 6.30-7.30pm - MVC architecture,routing,ADO.NET |  | 1 hour
|  | 11-12 pm-Checking the responsiveness of the page and implemented List Pages |  | 1 hour

## 28-04-2022
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Atsaya | learned entity relationships(one to one) | Project | 8:35 | 9:10 | 0:35 | Split | Time | Project
| Standup Meeting | Meeting | 9:10 | 9:30 | 0:20 | Project | 4:05 | Non Project
| learned entity relationships(one to many,many to many),fluent api | Project | 9:30 | 10:30 | 1:00 | Non Project | 0:30 | Exploration
| Morning Break | Lunch and Break | 10:30 | 10:50 | 0:20 | Exploration | 1:20 | Meeting
| learned fluent api | Project | 10:50 | 11:30 | 0:40 | Meeting | 1:15 | Customer Review
| Timesheet | Non Project | 11:30 | 12:00 | 0:30 | Customer Review | 0:40 | Lunch and Break
| Learned API | Project | 12:00 | 12:30 | 0:30 | Lunch and Break | 1:30
| Estimation | Project | 12:30 | 13:10 | 0:40 | TOTAL | 9:20
| Lunch | Lunch and Break | 13:10 | 13:50 | 0:40
| Estimation | Project | 13:50 | 14:30 | 0:40
| Team Review | Meeting | 14:30 | 14:55 | 0:25
| Meeting with Rafi | Customer Review | 15:00 | 15:40 | 0:40
| Session on angular | Exploration | 15:40 | 17:00 | 1:20
| Evening Break | Lunch and Break | 17:00 | 17:30 | 0:30
| Meeting with team | Meeting | 17:30 | 18:00 | 0:30
Ajay Bharathi | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| EF core | Exploration | 9:35 | 10:40 | 1:05 | Project | 2:40
| Morning Break | Lunch and Break | 10:40 | 11:00 | 0:20 | Non Project | 0:00
| Timesheet And Satisfaction Instruction | Meeting | 11:12 | 11:20 | 0:08 | Exploration | 2:23
| Sample Web api | Project | 11:20 | 12:00 | 0:40 | Meeting | 1:23
| Timesheet | Project | 12:00 | 12:13 | 0:13 | Customer Review | 0:42
| Sample Web api | Project | 12:13 | 12:30 | 0:17 | Lunch and Break | 1:15
| Estimation | Project | 12:30 | 13:00 | 0:30 | TOTAL | 8:23
| Lunch | Lunch and Break | 13:00 | 13:30 | 0:30
| Estimation | Project | 13:30 | 14:30 | 1:00
| Team Review | Meeting | 14:30 | 14:55 | 0:25
| Rafi Meeting | Customer Review | 14:58 | 15:40 | 0:42
| angular session with Saraswathi | Exploration | 15:42 | 17:00 | 1:18
| Evening Break | Lunch and Break | 17:00 | 17:25 | 0:25
| Team Meeting | Meeting | 17:30 | 18:00 | 0:30
Aravinth | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| Working on Requester list table page | Project | 9:30 | 10:50 | 1:20 | Project | 6:05
| Tea break and rafi's Speech | Lunch and Break | 10:55 | 11:20 | 0:25 | Non Project | 0:00
| Requester List table(Alignments) | Project | 11:25 | 12:20 | 0:55 | Exploration | 1:15
| Time Sheet | Project | 12:20 | 12:35 | 0:15 | Meeting | 0:45
| Add Request Page | Project | 12:35 | 13:15 | 0:40 | Customer Review | 0:40
| Lunch | Lunch and Break | 13:15 | 13:45 | 0:30 | Lunch and Break | 0:55
| Alignement and responsiveness in requester pages | Project | 13:45 | 14:25 | 0:40 | TOTAL | 9:40
| Review Meeting with team | Meeting | 14:30 | 14:55 | 0:25
| Review Meeting with rafi | Customer Review | 15:00 | 15:40 | 0:40
| Angular Session | Exploration | 15:45 | 17:00 | 1:15
| Working on table expansion responsiveness | Project | 17:05 | 18:35 | 1:30
| MOM entered | Project | 18:45 | 18:55 | 0:10
| Dropdown in requester list table page | Project | 18:55 | 19:30 | 0:35
Working on requester list table page(content changes)
| Working on Add request (responsiveness) |  |  |  | 0:00
Archana | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| Approver Page | Project | 9:30 | 11:00 | 1:30 | Project | 5:55
| Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 0:00
| Approver page with modal | Project | 10:45 | 11:30 | 0:45 | Exploration | 0:45
| checked responsiveness | Project | 11:30 | 13:00 | 1:30 | Meeting | 0:50
| Lunch | Lunch and Break | 13:00 | 14:00 | 1:00 | Customer Review | 0:40
| Review with team | Project | 14:00 | 14:55 | 0:55 | Lunch and Break | 1:15
| Review with customer | Customer Review | 15:00 | 15:40 | 0:40 | TOTAL | 9:25
| Angular session with Saraswathi | Project | 15:45 | 17:00 | 1:15
| Meeting with team | Meeting | 17:30 | 18:00 | 0:30
| Bootstrap tutorial(Container,grid basics,tables,images,buttons,typography,colors) | Exploration | 20:00 | 20:45 | 0:45
0:00
0:00
0:00
0:00
Aakaash | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| Exploring Dashboard Templates | Project | 9:33 | 10:25 | 0:52 | Project | 6:24
| Morning Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:20
| Dashboard Implementation | Project | 15:45 | 17:02 | 1:17 | Exploration | 0:00
| Lunch | Lunch and Break | 13:00 | 13:40 | 0:40 | Meeting | 0:20
| Customer meeting | Customer Review | 14:58 | 15:38 | 0:40 | Customer Review | 0:40
| Angular session with Saraswathi | Non Project | 15:42 | 17:02 | 1:20 | Lunch and Break | 1:10
| Evening Break | Lunch and Break | 17:05 | 17:20 | 0:15 | TOTAL | 9:54
| Enhancing Dashboard | Project | 17:30 | 19:00 | 1:30
| Explored Search box on DataTables & Auto complete Search box | Project | 20:45 | 23:30 | 2:45
0:00
0:00
0:00
0:00
0:00
Jeevanantham N | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| Modify Table Design Employee | Project | 9:31 | 10:00 | 0:29 | Project | 3:28
| Learn Web API Sample Program | Project | 10:00 | 11:00 | 1:00 | Non Project | 0:00
| Morning Break | Lunch and Break | 11:00 | 11:30 | 0:30 | Exploration | 3:09
| Alignment For Approver | Project | 11:31 | 12:00 | 0:29 | Meeting | 1:19
| Publish and Connect all Pages | Project | 12:00 | 13:10 | 1:10 | Customer Review | 0:40
| Lunch Break | Lunch and Break | 13:10 | 14:10 | 1:00 | Lunch and Break | 2:00
| Continue Connect and Create a dummy Page to Navigate all folders | Project | 14:10 | 14:30 | 0:20 | TOTAL | 10:36
| review with team | Meeting | 14:30 | 15:00 | 0:30
| Meeting with Rafi | Customer Review | 15:00 | 15:40 | 0:40
| Technical session on Angular(Basic, Typescript Sample) | Exploration | 15:50 | 17:00 | 1:10
| Evening Break | Lunch and Break | 17:00 | 17:30 | 0:30
| Meeting with Team for layout and web API | Meeting | 17:31 | 18:00 | 0:29
| Sample Program API for Employee Models, DbContext | Exploration | 22:00 | 23:59 | 1:59
0:00
Karthickraja | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| home page alignment (filters) | Project | 9:35 | 10:25 | 0:50 | Project | 5:00
| Morning Break | Lunch and Break | 10:15 | 10:30 | 0:15 | Non Project | 0:15
| home page alignment (card) | Project | 10:35 | 11:15 | 0:40 | Exploration | 1:18
| home page alignment (footer) | Project | 11:15 | 11:30 | 0:15 | Meeting | 0:45
| Time sheet | Non Project | 11:30 | 11:45 | 0:15 | Customer Review | 0:40
| learned on bootstrap css | Project | 11:45 | 13:00 | 1:15 | Lunch and Break | 1:15
| Lunch | Lunch and Break | 13:00 | 13:30 | 0:30 | TOTAL | 9:13
| working in the responsiveness(home page) | Project | 14:00 | 14:30 | 0:30
| review with team | Meeting | 14:30 | 14:55 | 0:25
| meeting with rafi | Customer Review | 15:00 | 15:40 | 0:40
| techinical session on angular | Exploration | 15:42 | 17:00 | 1:18
| Evening Break | Lunch and Break | 17:00 | 17:30 | 0:30
| Meeting with Team | Project | 17:30 | 18:00 | 0:30
| working in the responsiveness(home page, morecomment page) | Project | 18:00 | 19:00 | 1:00
Logesh Kumar | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| Home page alignment (filters) | Project | 9:30 | 10:30 | 1:00 | Project | 5:15
| Morning Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:30
| Home Page Responsiveness | Project | 10:45 | 12:00 | 1:15 | Exploration | 1:20
| Html page flow | Project | 12:00 | 13:00 | 1:00 | Meeting | 0:45
| Lunch Break | Lunch and Break | 13:00 | 13:30 | 0:30 | Customer Review | 0:40
| Assignment File upload(College) | Non Project | 13:30 | 14:00 | 0:30 | Lunch and Break | 1:00
| Timesheet | Non Project | 14:00 | 14:30 | 0:30 | TOTAL | 10:30
| Team Review | Meeting | 14:30 | 14:55 | 0:25
| Meeting with Rafi | Customer Review | 15:00 | 15:40 | 0:40
| Angular session | Exploration | 15:40 | 17:00 | 1:20
| Evening Break | Lunch and Break | 17:00 | 17:15 | 0:15
| Meeting with Team | Non Project | 17:30 | 18:00 | 0:30
| Responsiveness in Layout | Project | 21:00 | 23:00 | 2:00
0:00
Madujith M A | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| Exploring Dashboard templates | Project | 9:30 | 10:30 | 1:00 | Project | 6:04
| Coffee Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:15
| Implementing the Dashboard template | Project | 10:45 | 12:59 | 2:14 | Exploration | 0:00
| Lunch | Lunch and Break | 13:00 | 13:30 | 0:30 | Meeting | 1:15
| Time sheet updation | Project | 13:35 | 13:55 | 0:20 | Customer Review | 0:40
| review with team | Meeting | 14:30 | 14:55 | 0:25 | Lunch and Break | 0:45
| Customer Meeting | Customer Review | 15:00 | 15:40 | 0:40 | TOTAL | 9:59
| Angular session with Saraswathi | Non Project | 15:45 | 17:00 | 1:15
| Meeting with Team for discussing about customer feedback | Meeting | 17:30 | 18:00 | 0:30
| Reading Canva JS docs | Project | 18:30 | 20:30 | 2:00
| Implementing the Dashboard animation | Project | 22:00 | 22:30 | 0:30
0:00
0:00
0:00
Vidhyapriya V | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| Admin List Pages | Project | 9:30 | 10:30 | 1:00 | Project | 5:15
| Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:15
| Rework on Layout | Project | 10:45 | 11:30 | 0:45 | Exploration | 0:00
| Checking for the responsiveness | Project | 11:30 | 12:30 | 1:00 | Meeting | 1:45
| Updated Timesheet | Project | 12:30 | 13:00 | 0:30 | Customer Review | 0:40
| Lunch Break | Lunch and Break | 13:00 | 14:00 | 1:00 | Lunch and Break | 1:15
| Review with the Team | Meeting | 14:00 | 14:55 | 0:55 | TOTAL | 10:10
| Review with the customer | Customer Review | 15:00 | 15:40 | 0:40
| Angular session with Saraswathi | Non Project | 15:45 | 17:00 | 1:15
| Meeting with the team | Meeting | 17:30 | 18:00 | 0:30
| Worked on table alignments in admin page | Project | 18:30 | 19:30 | 1:00
| Worked on admin view pages | Project | 21:00 | 22:00 | 1:00

## 29-04-2022
Resource | Task Name | Task Type | Start Time | End Time | Total Time
Atsaya | Created API | Project | 8:30 | 9:30 | 1:00 | Split | Time | Project
| Soft Skill Session | Non Project | 9:35 | 10:30 | 0:55 | Project | 5:20 | Non Project
| Morning Break | Lunch and Break | 10:30 | 10:55 | 0:25 | Non Project | 1:40 | Exploration
| API migration for organisation,department,designation | Project | 10:55 | 13:10 | 2:15 | Exploration | 0:00 | Meeting
| Lunch | Lunch and Break | 13:10 | 13:45 | 0:35 | Meeting | 1:40 | Customer Review
| Timesheet | Non Project | 13:45 | 14:00 | 0:15 | Customer Review | 0:50 | Lunch and Break
| Estimation | Project | 14:00 | 14:35 | 0:35 | Lunch and Break | 1:25
| Review with team,discussed context,checked timesheet updation | Meeting | 14:35 | 15:35 | 1:00 | TOTAL | 10:55
| Idle(Waited for meeting with rafi) | Non Project | 15:35 | 16:05 | 0:30
| Meeting with rafi | Customer Review | 16:05 | 16:55 | 0:50
| Team Rank Discussion with rafi | Meeting | 16:55 | 17:05 | 0:10
| Evening Break | Lunch and Break | 17:05 | 17:30 | 0:25
| Team Meeting | Meeting | 17:30 | 18:00 | 0:30
| Explored and Tried API for organisation | Project | 19:00 | 20:30 | 1:30
| API for department | Project |  |  | 0:00
Ajay Bharathi | Absent |  |  |  | 0:00 | Split | Time
| Logging( In-Progress ) |  |  |  | 0:00 | Project | 0:00
| Exception Handling( In-Progress ) |  |  |  | 0:00 | Non Project | 0:00
[5 empty] | 0:00 | Exploration | 0:00
[5 empty] | 0:00 | Meeting | 0:00
[5 empty] | 0:00 | Customer Review | 0:00
[5 empty] | 0:00 | Lunch and Break | 0:00
[5 empty] | 0:00 | TOTAL | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
Aravinth | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| Working on Requester list table page | Project | 9:30 | 10:50 | 1:20 | Project | 6:05
| Tea break and rafi's Speech | Lunch and Break | 10:55 | 11:20 | 0:25 | Non Project | 0:00
| Requester List table(Alignments) | Project | 11:25 | 12:20 | 0:55 | Exploration | 1:15
| Time Sheet | Project | 12:20 | 12:35 | 0:15 | Meeting | 0:45
| Add Request Page | Project | 12:35 | 13:15 | 0:40 | Customer Review | 0:40
| Lunch | Lunch and Break | 13:15 | 13:45 | 0:30 | Lunch and Break | 0:55
| Alignement and responsiveness in requester pages | Project | 13:45 | 14:25 | 0:40 | TOTAL | 9:40
| Review Meeting with team | Meeting | 14:30 | 14:55 | 0:25
| Review Meeting with rafi | Customer Review | 15:00 | 15:40 | 0:40
| Angular Session | Exploration | 15:45 | 17:00 | 1:15
| Working on table expansion responsiveness | Project | 17:05 | 18:35 | 1:30
| MOM entered | Project | 18:45 | 18:55 | 0:10
| Dropdown in requester list table page | Project | 18:55 | 19:30 | 0:35
Working on requester list table page(content changes)
| Working on Add request (responsiveness) |  |  |  | 0:00
Archana | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| Approver Page | Project | 9:30 | 11:00 | 1:30 | Project | 5:55
| Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 0:00
| Approver page with modal | Project | 10:45 | 11:30 | 0:45 | Exploration | 0:45
| checked responsiveness | Project | 11:30 | 13:00 | 1:30 | Meeting | 0:50
| Lunch | Lunch and Break | 13:00 | 14:00 | 1:00 | Customer Review | 0:40
| Review with team | Project | 14:00 | 14:55 | 0:55 | Lunch and Break | 1:15
| Review with customer | Customer Review | 15:00 | 15:40 | 0:40 | TOTAL | 9:25
| Angular session with Saraswathi | Project | 15:45 | 17:00 | 1:15
| Meeting with team | Meeting | 17:30 | 18:00 | 0:30
| Bootstrap tutorial(Container,grid basics,tables,images,buttons,typography,colors) | Exploration | 20:00 | 20:45 | 0:45
0:00
0:00
0:00
0:00
Aakaash | Publish page | Project | 8:45 | 9:30 | 0:45 | Split | Time
| Soft Skill Session with Savitha on Problem Solving | Project | 9:32 | 10:25 | 0:53 | Project | 4:03
| Morning Break | Lunch and Break | 10:35 | 10:50 | 0:15 | Non Project | 0:00
|  | Project | 11:00 | 11:15 | 0:15 | Exploration | 0:40
| Exlored Angular on Dependency Injection & CLI | Exploration | 13:00 | 13:40 | 0:40 | Meeting | 0:00
| Estimation | Project | 14:58 | 15:38 | 0:40 | Customer Review | 0:49
| Lunch Break | Lunch and Break | 15:42 | 17:02 | 1:20 | Lunch and Break | 1:50
|  | Lunch and Break | 17:05 | 17:20 | 0:15 | TOTAL | 7:22
| Enhancing Dashboard | Project | 17:30 | 19:00 | 1:30
| Customer Meeting | Customer Review | 16:04 | 16:53 | 0:49
0:00
0:00
0:00
0:00
0:00
Jeevanantham N | Learn EntityFramework Core | Exploration | 9:00 | 9:30 | 0:30 | Split | Time
| Soft Skill Session with Savitha | Non Project | 9:31 | 10:30 | 0:59 | Project | 6:08
| Morning Break | Lunch and Break | 10:31 | 10:50 | 0:19 | Non Project | 1:13
| Web API Created and Adding Models( Organisation, Department, Designation ) | Project | 10:51 | 11:30 | 0:39 | Exploration | 0:30
| Review HTML Pages and Changes(Awardee Details, Employee Table) | Project | 11:31 | 12:10 | 0:39 | Meeting | 1:28
| Web API Migration ( Organisation, Department, Designation ) | Project | 12:11 | 13:20 | 1:09 | Customer Review | 0:50
| Lunch Break | Lunch and Break | 13:10 | 14:00 | 0:50 | Lunch and Break | 1:33
| Adding additional html pages in git and set the pages to Navigate all folders | Project | 14:01 | 14:30 | 0:29 | TOTAL | 11:42
| Review with team | Meeting | 14:31 | 15:35 | 1:04
| Meeting with Rafi - IDLE(30 mins waiting) | Customer Review | 16:05 | 16:55 | 0:50
| Notice Board Disucussion with Rafi | Non Project | 16:56 | 17:10 | 0:14
| Evening Break | Lunch and Break | 17:11 | 17:35 | 0:24
| Team Meeting Discussion for What We Do next | Meeting | 17:36 | 18:00 | 0:24
| Clone and work with Services for Base And Completed the GetID, GetAll, Create | Project | 20:47 | 23:59 | 3:12
0:00
Karthickraja | working on more comment page | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Soft skill Session with Savitha | Non Project | 9:35 | 10:30 | 0:55 | Project | 6:40
| Morning Break | Lunch and Break | 10:30 | 10:55 | 0:25 | Non Project | 1:25
| home page responsiveness | Project | 10:55 | 12:00 | 1:05 | Exploration | 0:10
| more comments responsiveness | Project | 12:00 | 13:00 | 1:00 | Meeting | 0:00
| Lunch Break | Lunch and Break | 13:00 | 13:30 | 0:30 | Customer Review | 0:50
| Time sheet updation | Project | 13:30 | 13:50 | 0:20 | Lunch and Break | 1:20
| Estimation | Project | 13:50 | 14:35 | 0:45 | TOTAL | 10:25
| Review with team(html layout,estimation,discussed context) | Project | 14:35 | 15:35 | 1:00
| Idle(Waited for the customer Review) | Non Project | 15:35 | 16:05 | 0:30
| Meeting with Rafi | Customer Review | 16:05 | 16:55 | 0:50
| team Rank discussion(rafi) | Exploration | 16:55 | 17:05 | 0:10
| evening Break | Lunch and Break | 17:05 | 17:30 | 0:25
| Team Meeting | Project | 17:30 | 18:00 | 0:30
|  | Project | 18:00 | 19:00 | 1:00
Logesh Kumar | Public Home Page | Project | 8:30 | 9:35 | 1:05 | Split | Time
| Soft Skill Session | Non Project | 9:35 | 10:30 | 0:55 | Project | 6:25
| Morning Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:35
| Html page flow | Project | 10:45 | 13:00 | 2:15 | Exploration | 1:00
| Lunch Break | Lunch and Break | 13:00 | 13:30 | 0:30 | Meeting | 0:30
| Timesheet | Project | 13:30 | 13:45 | 0:15 | Customer Review | 0:48
| Html Review | Project | 13:45 | 15:00 | 1:15 | Lunch and Break | 1:05
| Review with team | Project | 15:00 | 15:35 | 0:35 | TOTAL | 11:23
| Idle(Waited for the customer Review) | Non Project | 15:35 | 16:05 | 0:30
| Meeting with Rafi | Customer Review | 16:05 | 16:53 | 0:48
| Team Rank discussion | Non Project | 16:55 | 17:05 | 0:10
| Evening Break | Lunch and Break | 17:05 | 17:25 | 0:20
| Team Meeting | Meeting | 17:30 | 18:00 | 0:30
| Bootstrap | Exploration | 21:00 | 22:00 | 1:00
| Responsiveness | Project | 22:00 | 23:00 | 1:00
Madujith M A | Team Meeting | Meeting | 9:10 | 9:30 | 0:20 | Split | Time
| Exploring Dashboard templates | Project | 9:30 | 10:30 | 1:00 | Project | 6:04
| Coffee Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:15
| Implementing the Dashboard template | Project | 10:45 | 12:59 | 2:14 | Exploration | 0:00
| Lunch | Lunch and Break | 13:00 | 13:30 | 0:30 | Meeting | 1:15
| Time sheet updation | Project | 13:35 | 13:55 | 0:20 | Customer Review | 0:40
| review with team | Meeting | 14:30 | 14:55 | 0:25 | Lunch and Break | 0:45
| Customer Meeting | Customer Review | 15:00 | 15:40 | 0:40 | TOTAL | 9:59
| Angular session with Saraswathi | Non Project | 15:45 | 17:00 | 1:15
| Meeting with Team for discussing about customer feedback | Meeting | 17:30 | 18:00 | 0:30
| Reading Canva JS docs | Project | 18:30 | 20:30 | 2:00
| Implementing the Dashboard animation | Project | 22:00 | 22:30 | 0:30
0:00
0:00
0:00
Vidhyapriya V | Admin View Pages | Project | 8:30 | 9:30 | 1:00 | Split | Time
| Softskill Session | Non Project | 9:35 | 10:30 | 0:55 | Project | 5:50
| Break | Lunch and Break | 10:30 | 10:45 | 0:15 | Non Project | 1:25
| Modifying List and View Pages | Project | 10:45 | 12:45 | 2:00 | Exploration | 0:00
| Updating Timesheet | Project | 12:45 | 13:00 | 0:15 | Meeting | 1:40
| Lunch | Lunch and Break | 13:00 | 14:00 | 1:00 | Customer Review | 0:50
| Checking the flow of the admin pages | Project | 14:00 | 14:35 | 0:35 | Lunch and Break | 1:35
| Review meeting with the team | Meeting | 14:35 | 15:35 | 1:00 | TOTAL | 11:20
| Idle(Waited for customer meeting) | Non Project | 15:35 | 16:05 | 0:30
| Meeting with Rafi | Customer Review | 16:05 | 16:55 | 0:50
| Team Rank discussion with Rafi | Meeting | 16:55 | 17:05 | 0:10
| Break | Lunch and Break | 17:10 | 17:30 | 0:20
| Team Meeting | Meeting | 17:30 | 18:00 | 0:30
| Worked on Edit Pages(admin) | Project | 18:30 | 20:00 | 1:30
| Intergrating all Pages(admin) | Project | 22:00 | 22:30 | 0:30