## Status Template - WEEK
Work Items | Completed | In Progress | Yet to start
Low Level Design | Sequence Diagram, Server side Validation, User Interface | HR sequence diagram,Client side Validation | Integration points,Session & Cache, Settings/Configurations
Web API Implementation | Completed all Api implementation | NIL | NIL
Angular Component Creation | Completed All Components creation | NIL | NIL
Web API and Angular Integration | Completed all Pages Integration. | Dashboard, Homepage | NIL
Unit Test Cases for Web API with Stubs and Mocks + Angular Component Testing | Unit test cases for Organisation , Award and department controllers | Test cases for Controllers and Service layer for All Services , Test cases for DAL layer | NIL
Refactoring and Deployment | NIL | NIL | Deployment
Test Scenarios and Test Case Preparation | NIL | NIL | Test Scenarios and Test Case Preparation
Application Testing and Defects Tracking and Fixing | NIL | NIL | Application Testing and Defects Tracking and Fixing
Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots | NIL | NIL | Release Artifacts, Source code, Development Setup Configuration Document, Build and Deployment Document, API Documentation, User Manual with Screen Shots